## punchlist
status | description | comments | date_orig | due_date | author_id | closure_id | supplier_id | system_id | floor_id | phase_id | cat_id | building_id | closed_by
0 | Bottom nozzle tolerance not possible to check because bottom valve is installed. | Valve is installed, no leakage recorded. Tolerance to be checked during commissioning. C. Fallet 05.Mar.2018: after talking to S. Hilfiger (weld and vessel inspector): checking of tolerance during commissioning not recommended, following rationale: 1. disassembly and re-assembly of the bottom valves has certain risk of damaging components. 2. tolerance is sufficient to fit the valve (as it is installed). 3. Pressure test was performed successfully. For that reason the punch is closed without any action taken. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Agitator not present; mixing group not possible to check. Flatness of flange not possible to check. | BLF to install the agitator. Mixing group to be checked by Arcade. Flatness of flange to be checked both on agitator flange and vessel flange by Arcade. RCAR 02-may-2018: Agitator has been found damaged (refer to the pictures attached). BLF has been sent the agitator to Ekato to fix the problem. Declared 2 weeks to have the agitator back. RCAR 29may2018: agitator installed according to NVS maintenance procedure. A scratch has been found on the flange inside the vessel. NVS verified it with Arcade considering the scratch acceptable since it could be very complicate to erase it and because it’s a little scratch. No other verifications are foreseen in Arcade scope. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Studs (goujon) too shorts on some nozzles | BLF to check and exchange them on site. / New studs longer have been installed on all the nozzles on the top tank. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Load cells not installed, no check done | load cells to be installed on site. RCAR 02-may-2018: Load cell have been installed. Cables conduits to be properly installed; XQUA 04-JUL-2018: specific NC point (N° 8798) opened for the issue of cables' conduits. This point can be closed | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Tolerance on diameter of ingold plugs not checked because final components not installed (sampling, conductivity, ..) | Test to be checked during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Degree of ingold port not aligned for the following nozzles: N86 (sample) nad N91 (spare) | Measured value (rounded down to full degrees) needs to be indicated on the vessel/GA drawing with a note “measured at FAT”. • N86: acceptable. • N91: spare, acceptable. Actual degree mesuared: N86 = - 0.57; N91 = 14.43. Fabiana Cortellini 10-AUG-2018: updated construciton drawing has been issued by Bilfinger and measured slopes indicated. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Dimensions of dip tube cannot be checked, sprayball internals not checked - sprayballs and dip tube not installed. | BLF to install the sprayballs and dip tube, check diptube dimensions and check internal surface of sprayballs (check no holes are blocked). Fabiana Cortellini 28-MAR-2018: sprayballs and diptube checked during SAT. Refer to protocol P16-0052-SAT MECHANICAL PROTOCOL R205. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | All tank nozzles and valves are not tagged | Final tags to be put in place on site, after tank installation Fabiana Cortellini 27-MAR-2018: refer to skid NC-34 (prolog 5302). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | ISO PC/D 205-6: one weld on Dip tube is temporary. | BLF to fix the welds on dip tube. Fabiana Cortellini 27-MAR-2018: the weld has been finalized. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | The following components are not installed and not available: V503 - P101 - W101 - X111 - Y811 & G811 - L111 - P102 - X101 - T101 - M101. | BLF to provide the instruments. / V503 installed. W101 refer to NC-0524. X111 refer to NC-8800. Y811 and G811 refer to NC-8777. L111 installed. P102 installed. X101 refer to NC-8790. T101 installed. M101 refer to NC-0522. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Instruments fitting not checked because istruments not available. | Fitting to be checked when instruments will be available Fabiana Cortellini 27-MAR-2018: instruments have been installed on site and fitting checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Vessel drawing is not in 'As built' revision | As built' revision to be included in the DOE by BLF. / Vessel drawing received in rev 2.0 as built (Passage TQC). Document in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Manufacturer's name plate is not available in the DOE | Manufacturer's name plate to be included in the DOE by BLF | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Insulation documents are not available | Insulation documents to be included in the DOE by BLF. / Novartis decided to insulate the skid on site. Responsibility of a different vendor. No doc to be added into the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Material certificate list, 2 items numbers are missing below items 12 and 14. | Add items numbers missing in the Material Cert. List Seun Idowu 12-APR-2018: Material cert. list updated. Entry error, the missing numbers for the items below items #12 and 14 are not required. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Material certificate list, item N39, Ht number for flange according to DIN 11864-3 and not for DIN 11864-2 | Update the Material Cert. List Seun Idowu 12-APR-2018: Material cert. list updated. Item #N39 flange specification changed to DIN 11864-3. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Material certificate list, item N80, standard- Ht Nb and cert. Nb are missing | Update the Material Cert. List Seun Idowu 12-APR-2018: Material cert. list updated. Material certificate checked and included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Material certificate list, item N15, the drawing Nb is missing | Add PC205 rev0.3 in the box Seun Idowu 12-APR-2018: Material cert. list updated. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Material certificate list, item N13, the drawing Nb-Standard-Ht Nb and cert. Nb are missing | Update the Material Cert. List Seun Idowu 12-APR-2018: Material cert. list updated. Material certificate checked and included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Material certificate of gaskets are missing: missing for the manhole and agitators. | Gaskets documents to be included in the DOE by BLF RCAR 29MAY2018: for the agitator, gasket cert was checked with NVS during the installation. Documentation collection into the VTOD to be verified. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Spray ball and diptubes documents are missing | Spray balls and diptubes documents to be included in the DOE by BLF Seun Idowu 15-MAY-2018: Spray balls and diptubes documents included in VTOD. Refer to R205 skid SAT protocol, section piping certificate material. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Items 25 and 26 for a te and a reduction are missing. | Update the Material Cert. List Seun Idowu 12-APR-2018: Material cert. list updated. Material certificates checked and included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Welding Log - Welds 405A to D are missing | Update the Material Cert. List Seun Idowu 12-APR-2018: Welding Log updated. Welds #405A to 405D deleted from the welding map and welding log. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Accessory welding documents are missing | Accessory welding documents to be included in the DOE Seun Idowu 15-MAY-2018: Accessory welding documents included in VTOD. Refer to R205 skid SAT protocol, section piping welding report. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Degreasing/passivation certificate is missing | Degreasing/passivation certificate to be included in the DOE by BLF Seun Idowu 12-APR-2018: Internal and external degreasing/passivation certificates are included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Flushing / drying procedure and certificates are missing | Flushing and drying certificate to be included in the DOE by BLF Fabiana Cortellini 28-AUG-2018: Flushing is included in the passivation procedure. Drying executed but not documented. Accepted by NVS (Zanobini email 25aug2018). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Notified Body's design examination is missing | Notified Body's examination design to be included in the DOE by BLF Seun Idowu 12-APR-2018: Notified body (TUVRheinland) test report - examination of design included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Notified Body's CE attestation is missing. This point is not blocking the MC. It's conditionally accepted by NVS management. | Notified Body's attestation to be included in the DOE by BLF. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Maintenance log is missing | Maintenance log to be included in the DOE by Novartis | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Weldings information (heat number and certificate number) missing on the isometrics. | Information to be filled in after completion of weldings Fabiana Cortellini 27-MAR-2018: diptube and sprayballs isometrics and heat number tables have been update and checked. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R205 test TS02.2.03. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | All lines are identified with a temporary label. | BLF to install final label on all the equipment/lines Fabiana Cortellini 27-MAR-2018: refer to skid NC-34 (prolog 5302). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Sprayball iso not according to the constructed piece: upper part longer. | BLF to update iso or modify the sprayballs tubes. Fabiana Cortellini 27-MAR-2018: ISO has been updated according to the installation. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Drainability test failed at the position of the blank flange (not according to same profile as the real flange on agitator). | Agitator to be mounted at site and drainability test to be repeated. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | CIP line number on Isometric for bottom valve ISO 40-BUFFER-EG16N40-R205-R205 does not match P&ID | BLF to update isometric to match P&ID Fabiana Cortellini 27-MAR-2018: bottom valve has been represented on the ISO 40-BUFFER-EG16N40-R205-002 folio 1/2. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Agitator not installed, test cannot be carried out | BLF to install agitator and perform test | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Agitator not installed, level strapping test carried out does not reflect true volumes | BLF to install agitator and reperform test | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Volumes measured do not match vessel drawing | Construction drawing, calculation note and nameplate to be updated accordingly. / Vessel drawing updated according to the FAT measurement. Rev 2.0 as built collected in the VTOD | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Sprayball documentations (drawings, iso,...) not aligned with try n°2 of sprayball coverage test. | Documents to be updated accordingly and BLF to garantee the exact installation of the spayball. Fabiana Cortellini 28-MAR-2018: Isometrics updated according to installation and checked during SAT. Refer to protocol P12-0052-SAT MECHANICAL PROTOCOL R205. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Construction drawing to be updated with modifications concerning the new agitator to be installed. | Drawing to be updated as per final configuration of agitator. / Construction drawing updated according to the info received from Agitec. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | Leak pressure test not performed | Test to be performed during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | n° 05, 16: hardware devices description in the wiring diagrams hardware list does not match with the installed hardware | wiring diagrams hardware list to be corrected MCHR 16-MAR-2018: Wiring diagrams corrected | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R205 - Buffer Preparation Tank 2000L | LEVEL 1 | SAT | B | Building 341
0 | n° 06: missing or wrong cable labels on the terminals inside control cabinet. | terminals labels to be put on the wires / Missing labels have been placed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 08, 14: some labels in the control cabinet are not correct (wrong description/wrong colors). | labels to be corrected / MCHR 06-JUL-2018: Labels have replaced. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 01: hardware documentation of electrical components of the cabinet is missing | hardware documentation to be provided and checked M.POZZI 13-MAR-2018: Hardware documentation provided | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: cabinet manufacturer's self-check sheet is missing | Whole cabinet builder test incl. declaration of conformity to be provided. MCHR 20-MAR-2018: Certificate provided for self-checks. CE certificate must be reissued with proper norms and titles. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 03: cabinet CE certificate is missing | certificate to be provided and checked MCHR 16-MAR-2018: certificate provided from SPIE | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 01: MCB after redundant 24V supply module shall be different type and not Schneider (rate is not correct) | Siemens type 5SY4220-5 to be provided and installed MCHR 19-MAR-2018: Cabinet submitted to notified body review. Result is that MCB shall be changed with Siemens type. MCB already replaced in cabinet, wiring diagrams updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: vent device with filter is to be installed on the cabinet to prevent overpressure in case of air leak on pneumatic circuit inside the cabinet | vent device with filter to be provided and installed M.CHRAPPAN 13-MAR-2018: Vent device installed | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 05: earthing of the skid: wiring of the earthing cable/cords on the skid is completely missing | Not compliant with Low Voltage Directive C15-100. Eearthing of the skid to be done and checked Preparing the skid for earthing must be finished at vendor site including measurement. MPOZZI 12-MAR-2018: Cord from Skid to Building earth provided | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 11: some cabling on instrument have been bent too much, this will damage the cable in a short time | cables to be adjusted properly on the skid / MCHR 06-JUL-2018: Cables have been refitted in field. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 08: PROFIBUS cable numbering is not as per Novartis procedure | wiring diagrams to be corrected, labels on cables to be done. / Clemessy will label the profibus cables. Wiring diagram will be updated accordingly and the verification will be done during SAT. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 10, 14: cable colors for 24V: brown is + white is - as per colour code: some cables on wiring diagram are inverted | wiring diagrams to be corrected, cabling in the cabinet to be inverted. / Wiring diagram updated accordingly. Document collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 01: instrument list not available; the test has been executed with the P&Ids as a reference document | instrument list to be provided and checked VS the P&ID M.POZZI 12-MAR-2018: Document provided, it has to be issued formally to JACOBS (missing doc. number, revision, vendor info) | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: instruments missing: bursting disk | instrument to be installed on skid and connected to control cabinet | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: TT101 (tank bottom temp): the wrong instruments type is installed (TR15 non aseptic instead of TM411 aseptic) | Correct type of transmitter is installed, only label must to be exchanged. M.POZZI 12-MAR-2018: Label exchanged. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | instrument configuration sheets are not available; the test cannot be executed | instrument configuration sheets to be provided and test to be executed / MCHR 06-JUL-2018: Configuration sheets are provided in rev. 0.1 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | (safety system - installation fallback) internal tests has not been verified during FAT. | entire tests to be repeated on site / MCHR 06-JUL-2018: Internal test of safety system performed on 24MAY2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 14: some wires are missing (field device not wired - V001, V922, V930, V963, V992, air supply - earth wire missing on XRINT.02) | cable to be layed down and connected to cabinet M.CHRAPPAN 09-MAR-2018: V001 connected, rilsan pipes for V922, V930, V963, V992 already pulled but not yet connected because actuators are not mounted. air supply is present Clemessy to install loto valves on V930, V963, V992 M.CHRAPPAN 19-APR-2018: Installation completed for all the points mentioned above | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 14: load cells are not installed under the tank, the wires are not layed down to the cabinet, the cable ways are not present on the skid | to lay down the cables and the cable ways (M.Pozzi 07-MAR-2018): load cells installed | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 06. wrong colour of terminal indicated on wiring diagram | wiring diagram to be corrected M.Pozzi 07-MAR-2018: wiring diagrams corrected, master copy with redmarks inside cabinet | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital input loop check failure: GSH-811 rupture disk: disk not installed | rupture disk and indicator to be installed and connected, test to be redone MCHR 19-MAR-2018: Rupture disk and sensor are connected / MCHR 06-JUL-2018: I/O test performed by NVS | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital output (on/off valves) loop check failure: V954, V961, V003, V004 valves not installed | valves to be installed and wired: test to be repeated / MCHR 09-JUL-2018: Valves installed and tested | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital output (on/off valves) loop check failure: V401, not possible to command it | test to be done on site / MCHR 09-JUL-2018: Valves tested by NVS | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital output (on/off valves) loop check failure: V701, pneumatic connetion on the valve is wrong | pneumatic connection on the valve to be fixed / MCHR 09-JUL-2018: Valves fixed and tested by NVS | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital output (on/off valves) loop check failure: V502, wrong connection on FESTO block | connection on FESTO block to be fixed / MCHR 09-JUL-2018: Valves fixed and tested | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital output (on/off valves) loop check failure: V001, V922, V930, V963, V992 are loose valves | test to be done on site / MCHR 24MAY2018: Loop check to be performed by Clemessy / MPO - 02aug2018: valves have been installed and connected see Clemessy CTOD Sec. 12.4 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 03: analogue input loop check failure: TT982, TT980: RM042 transducer in the cabinet not configured | transducer to be configured / MCHR 10-JUL-2018: Device report for TT982, TT980 attached to SAT. IO check was done by NVS with no issues. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 04: analogue output (control valve) loop check failure: R701: valve actuator seems not properly configured | valve actuator to be configured / MCHR 09-JUL-2018: Valves configured and tested | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 03: analogue input loop check failure: W101: weighing cells not installed and not wired | weighing cells will be installed and wired at site; test to be done on site RCAR 11JUL2018: weighting cells installed and wired; I/O check performed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | cabinet is not clean, lot of construction material is around | cleanliness of cabinet to be checked on site Tuesday 27-MAR-2018: Cabinet has been cleaned by SPIE | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: missing information on the CE label: max Icc that the cabinet can sustain. A second label with the client data is missing | labels to be corrected/added M.Pozzi 07-MAR-2018: Label with max Icc provided XQUA 04-JUL-2018: All the labels are present and conform | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 09: poor fixing of part of the piping/cable trays supports on the top of the buffer storage tanks | supports to be analysed and in case reinforced. / Support installed on the ceiling of the room to properly fix the frame. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 11/TS02.3.05: due to the works in progress it is not possible to check cable trays completeness, clashes and interference, holes and openings | checks to be done when construction activities are completed / MCHR 06-JUL-2018: Cable trays are complete | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 12/TS02.3.05 - n° 03: some rilsan pipes are touching CIP pipes - near valve V952 T980 cable is touching the steam pipe. | rilsan pipes to be repositioned / MCHR 06-JUL-2018: Rilsan pipes have been repositioned. T980 cable rearranged on support | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | this test refers to the check of the calibration of instruments, it is not foreseen during FAT | test to be done on site / NVS will perform all calibration activities | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 14: the cabling of the terminal block XREXT.03 is done in a different way from the other cabinets, this is not good for maintenance. | cabling to be changed as per other cabinets; also wiring diagrams to be corrected also. MCHR 06-JUL-2018: Cabling has been arranged as per B155. Folio 051 have commented in relation to Watchdog cable info (Wiring diagram to be updated see #11033). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: the profibus address of Festo block is wrong | wiring diagram to be corrected with the Profibus address indicated in the I/O list and micro swith configuration on device to be changed. MCHR 10-JUL-2018: Profibus address is corrected on I/O list and Switch configuration | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | LOTO valves not installed | BLF to install them, Jacobs/Novartis to check the installationa dn the electrical wiring diagrams MCHR 16-MAR-2018: Loto valves installed for valve inside BLF scope | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | To perform passivation, the mechanical interlock on the Festo Clusters is removed to operate the valves. | BLF to check if some plastic interlocks have been damaged or lost and replace them. Fabiana Cortellini 02-AUG-2018: I/O check performed and no issues were communicated. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | All lines are identified with a temporary label; some of the components are identified with temporary label; Few components are not identified. | BLF to install final label on all the equipment/lines. / RCAR 02JUL2018: All components are identified with temporary labels, some are permanently connected. / all the components have been tagged; Refer to NC-11320 for the labeling. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-BUFFER-EG16N40-B204-O41 folio 1 of 2: line partially not installed. | BLF to install the line and check to be performed. / Line has been installed and verified according to the ISO. ISO will be collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Weldings information (heat number, certificate) missing on the isometrics. | BLF to update iso with these information. / All the ISO have been completed with the heat numbers (a dedicated table is attached to the specific ISO - when it's required). Check has been done by BLF. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-CIPR-EG16N40-B204-048 folio 1 of 1: Slope on flexible X961 not verified because not installed. | BLF to complete installation. Fabiana Cortellini 07-DEC-2017: The flexible X961 has been installed and connected. The slope has the good direction and the good value: 3,9%. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 40-CIPR-EG16N40-B204-049 folio 1 of 1: Slope on flexible X941 not verified because not installed. | BLF to complete installation. Fabiana Cortellini 07-DEC-2017: The flexible X941 has been installed and connected. The slope has the good direction and the good value: 2,7%. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 40-ERF-EG16N40-B204-060 folio 1 of 2: Slope on flexible X702 not verified because not installed. | BLF to complete installation. / Flexible installed. Direction of the slope according to the ISO. Value is not needed to be recorded (non-GMP pipe). ISO is collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-BUFFER-EG16N40-B204-050 folio 2 of 3: Slope on flexible X401 not verified because not installed. | BLF to complete installation. Fabiana Cortellini 07-DEC-2017: The flexible X401 has been installed and connected. The slope has the good direction and the good value: 3,9%. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 40-ACP-EG16N40-B204-043 folio 2 of 2: Pressure Indicator P-500 missing on the filter F1 top. | BLF to install the PI. Fabiana Cortellini 07-DEC-2017: The manometer P500 is installed on the filter F1. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-CIPR-EG16N43-B204-051 folio 2 of 2: line not installed. | BLF to complete installation on site. / Line has been installed and verified according to the ISO. ISO is collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 15-G-N2P-EG18X40-B204-061 folio 1 of 1: line not installed. | BLF to complete installation on site. Line installed; installation checked during WD1 with Bilfinger according to the P&ID. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-CIP-EG16N40-B204-088 folio 1 of 1: line not installed. | BLF to complete installation on site. Fabiana Cortellini 07-DEC-2017: The line has been installed and the isometric checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-CIP-EG16N40-B204-188: line not installed, iso not available. | Line will be installed directly on site. BLF to provide ISO. / Line has been installed. It's part of the CIP test pack. Installation will be verified accordingly. Documentation will be collected into the related test pack (CIP B293). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | On the Equipment List line numbers not compliant with P&ID and few datasheet revision not compliant with the datasheets. | BLF to update Equipment List Fabiana Cortellini 21-NOV-2017: The Equipment List has been updated in rev 1.04 and checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Reference on equipment list for Manual Ball Valve Mecainox cannot be verified on istalled valve. | BLF to verify and update the reference column in the equipment list. Fabiana Cortellini 26JAN2018: Reference is readable on the Datasheet only. PN4 is valves installed on hygienic pipes (valve is characterized by a greater length of the piece welded to the two sides of the body and by the incision on the body of the valve, as well as from the data of the roughness found on the pipe); PS4 is for the valves installed on non-hygienic pipes. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Isometrics not conform to the P&ID: some lines indicated with different numbers. | NVS to update the P&ID accordingly (rev. 3.1): some line numbers to be deleted and some lines to be updated accordingly. P&ID to be updated adding the new flange on line 40-CIP-EG16N40-B204-049 (for handling reason). RCAR 11JUL2018: P&ID red marked updated after WD2. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Weld numbers for the welds done directly on the skid (between two different isos) missing on the ISO. | BLF to update ISOs with the missing information. / All the ISOs have been updated including the welds numbers missing during FAT phase. All the ISOs will be collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Continuity not according to P&ID | BLF to update ISO / All the ISO have been updated according to the P&ID. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 40-CIP-EG16N40-B204-049 to be updated with the new flange added for handling reason. | BLF to update the ISO. / ISO has been updated according to the installation. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | P&ID to be updated adding the new flange on line 40-CIP-EG16N40-B204-049 (for handling reason). | NVS to update the P&ID. / Refer to NC-0614 for the closure. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | risk assessment not available | BLF to provide the document. / Risk assessment availability is a test included into the SAT protocol. Refer to the SAT protocol for the test performing and conformity. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Welder qualification test certificate report YAL is missing. | Update the Welding book Fabiana Cortellini 21-NOV-2017: Welder qualification test certificate report YAL is available in the Welding book. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Isometrics for Line 40-VP2-EG16N44-B204-076 and 8-VP2-EG16N44-B204-099 are missing. | BLF to generate isometrics. Fabiana Cortellini 21-NOV-2017: Isos have been created in rev 1.0. To be checked on site against installation. RCAR 02JUL2018: All these lines are part of the fluid test pack. Refer to the relative test pack for the evidence and refer to the fluid system for any punch opened. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #H505, SG012, V922, V930, V963, V992, X101 and X811 : Certificate numbers missing hence unable to view VTOD. | BLF to update Equipment List BLF to include in VTOD Documentation for SG012 has been provided and checked this item is closed. V922,V930,V963 transferred to CIP system B293. V992 Transferred to CIP system B292. H505 transferred to system AR. Certification and Documentation checks for these items to be verified at SAT within the system that they have been transferred to. Novaseptum X101 and Angst/Pister X811 certificate numbers still missing from equipment list, unable to check documentation for these items. This action still outstanding. AWH to provide certificate of roughness as certificate not present in file. Item X101, sampling port to be purchased by Novartis hence documentation for this item will be checked by Novartis. F Burrows 20-Mar-2018 RCAR 07aug2018: certificates collected in the VTOD Material Certificates and Equipment List updated accordingly. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item # X101 : Material certificate 3.1 is not identified on equipment list | Add Material Cert. in the VTOD and update the Equipment List Material certification shall be checked and verified when documentation for X101 from vendor NovaSeptum is provided. This punch item is now closed, The tracking and verification has been transferred to prolog number 0622. Freda Burrows 20-Mar-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #XP102, P103, P500, X501 and X922 : Error on the equipment list. Material Certificate 2.1 is not available. | BLF to update Equipment List Fabiana Cortellini 21-NOV-2017: The Equipment List has been updated in rev 1.04 and checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #X922 : FDA certificate not identified on equipment list | BLF to update Equipment List This equipment has been moved to system VP2. The equipment list and associated documentation for X922 shall be checked and verified with the system that it has been transferred to. Freda Burrows 20-Mar-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #H920, H922, H923, V503, X501 and X922 : BSE certificate not identified on equipment list | BLF to update Equipment List Equipment list has now been updated to include BSE Certification for H920,H922,V503,X501. X922 has been transferred to system VP2 the equipment list for this item shall be checked in system VP2. Freda Burrows 20-Mar-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #V401, V503, X922, X071 and X072 : Roughness certificate not identified on equipment list | BLF to update Equipment List Equipment list has now been updated to include Roughness certificate V401,V503 X701 and X702. X922 has been transferred to system VP2 the equipment list for this item shall be checked in system VP2. Freda Burrows 20-Mar-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #V401, V503, X501 and X922 : EP certificate not identified on equipment list | BLF to update Equipment List Equipment list has now been updated to include EP Certification for V401, V503, and X501. X922 has been transferred to system VP2 the equipment list for this item shall be checked in system VP2. Freda Burrows 20-Mar-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #H501, H504 and P103 and X504 : Heat number incorrect on equipment list | BLF to update Equipment List . / equipment list updated and collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #H920, H922, H923, LG013, V701, X504, X922 and Y811 : Heat number not identified on equipment list | BLF to update Equipment List / equipment list updated and collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Technical documentation (manual, operating instruction) missing | Insert Technical documentation in the VTOD /All the technical documents have been included in the VTOD section 2. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Isometrics for Line 40-VP2-EG16N44-B204-076, 8-VP2-EG16N44-B204-099 and 50-CIP-EG16N40-B204-188 are missing. | BLF to generate isometrics. Fabiana Cortellini 21-NOV-2017: Isos have been created in rev 1.0. To be checked on site against installation. RCAR 02JUL2018: All these lines are part of the fluid test pack. Refer to the relative test pack for the evidence and refer to the fluid system for any punch opened. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Test TS01.2.12 - Borescope videos missing for various welds on the following isometric: welds #7, 22, 24 and 33 on ISO 50 BUFFER-EG16N40-B204-041 Folio 1/2 welds #2, 4 and 7 on ISO 50-BUFFER-EG16N40-B204-041 Folio 2/2 welds #2, 4 and 5 on ISO 15-ACP-EG16N43-B204-045 Folio 1/1 welds #1, 8, 12, 14, 16 and 17 on 50-CIPR-EG16N40-B204-048 Folio 1/1 welds #11, 13, 15 and 18 on ISO 40-CIP-EG16N40-B204-049 Folio 1/1 welds #1, 2, 3 and 4 on ISO 50-BUFFER-EG16N40-B204-050 Folio 1/3 weld #12 on ISO 50-CIPR-EG16N43-B204-051 Folio 1/2 welds #1 and 2 on 50-CIP-EG16N40-B204-088 Folio 1/1 | BLF to provide videos and independent weld inspector (Arcade engineering) to review the borescope videos. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 40-ACP-EG16N43-B204-044 Folio 1 : Weld #04, welding information missing from welding book | BLF to update welding book with the missing welding information Fabiana Cortellini 21-NOV-2017: The welding information is available on the welding book (A200). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Test TS01.2.12 - No access to conduct visual and video borescope checks for various welds on the following lines: welds #5, 6, 7 on ISO 50-CIPR-EG16N40-B204-048 Folio 1/1 weld #9 on ISO 40-CIP-EG16N40-B204-049 Folio 1/1 | The weld to be checked for imperfections by the independent weld inspector to guarantee the weld robustness and to ascertain its quality level. Orbital welds: borescope videos for preceding and subsequent welds to be checked. RCAR 09jul2018: Inspector from Arcade has checked the welds/coupon/welders doc and the above welds have been considered ok. The weld #9 of line -049 is an orbital and the Inspector confirmed it's ok. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-CIPR-EG16N43-B204-051 Folio 2, Welds #5, 6 : welds to be executed on construction site | BLF to perform the welds on site and to update welding book with the information. / All the welding doc related to this system is completed and collected into the SAT protocol (and VTOD). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | BSE/TSE free certificate and FDA (or USP) certificate missing for all the gaskets installed on pipes. | BLF to provide the certificates Mario Luiso 06-JUL-2018: BSE/TSE free certificate and FDA (or USP) available, checked and inserted in VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | test not completely performed, gasket material not checked. | Check all gasket material according to pipe class Mario Luiso 06-JUL-2018: All gaskets material checked on isometric nomenclature document. Gasket material verified according to the Novartis specification document for each pipe class. EPDM or PTFE suitable for piping class EG16N43, EG16N44 and EG16N46. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | some heat numers missing on the isometric nomenclature document. | BLF to update the document. / All the ISO have been completed with the heat numbers (a dedicated table is attached to the specific ISO - when it's required). Check has been done by BLF. Documentation is collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Test TS01.2.12 - on the weld log RTU-PR-S-121, the column C/NC (checked/non checked) is not ticked on the following isometrics: 50-BUFFER-EG16N40-B204-041 Folio 1/2 10-ACP-EG16N40-B204-043 Folio 1/1 40-ACP-EG16N40-B204-043 Folio 2/2 50-CIPR-EG16N40-B204-048 Folio 1/1 8-CIP-EG16N40-B204-049 Folio 1/1 40-CIP-EG16N40-B204-049 Folio 1/1 50-CIPR-EG16N43-B204-051 Folio 2/2 | BLF to update weld log document RTU-PR-S-121 and independent weld inspector (Arcade engineering) to check the weld log document. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Line 40-CIP-EG16N40-B204-049: second flange to be added for maintenance of the flange already installed below valve V931. | Flange to be installed on site and local passivation to be performed. / Flange installed, ISO updated accordingly; passivation performed and documented (weld done 31-Jul; passivation done week 4-Augt). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Safety clamp not installed on the top of the filter F1 (manometer nozzle). | BLF to install the safety clamp on site (manometer dismounted for transportation) / Manometer in place and Safety clamp installed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Pressure test on lines performed according to fluid list pressure values, but documentation missing. | BLf to provide the documentation. / documentation available. Verification has been done during SAT. Refer to the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Studs (goujon) too shorts on some nozzles | BLF to check and exchange them on site. / All the studs have been installed properly with the correct length. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Load cells not installed, no check done | load cells to be installed on site. / Load cell installed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Tolerance on diameter - sprayballs and diptube not installed | BLF to install the sprayballs and diptube. / Sprayball and dip tube installed and checked according to the ISO. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Tolerance on diameter of ingold plugs not checked because final components not installed (sampling, conductivity, ..) | Test to be checked during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Sprayballs missing | To be provided by BLF. / Sprayballs installed and verified according to the ISOs collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Degree of ingold port not aligned for the following nozzles: N79 (spare); N89 (spare). | Measured value (rounded down to full degrees) needs to be indicated on the vessel/GA drawing with a note “measured at FAT”. • N79 and N89: spare nozzle: not critical. Fabiana Cortellini 03-APR-2018: construction drawing has been issued by BLF in rev 2.1, checked and approved with "no comment". | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | The following components are available but not installed: P101 - L111 - P102 - P103 - Y811 + dip tube on nozzle N25 and sprayball on nozzle N39. | Components to be installed on site, after tank installation. / All the components listed are installed. Refer to NC-11009 for the novaseptum. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | The following components are not available: W101 - X111 - G811 - X101 - manway sight glass | Components to be provided and installed. / all the components are installed. For the Novaseptum refer to NC-11009 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | All tank nozzles, Valves and outlet line are not tagged. | Final tags to be put in place on site, after tank installation. RCAR 02JUL2018: nozzles tag to be put in place: all the components are tagged (temporary or permanently); labels in progress (not critical). RCAR 22aug2018: nozzles tags installed; permanently tags installed. Labeling not in the scope of BLF1. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | weldings information (heat number and certificate number) missing on the isometrics. | Information to be filled in after completion of weldings. / All the ISOs have been completed with the heat numbers (a dedicated table is attached to the specific ISO - when it's required). All the welds number is recorded on the last ISO revision. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Fitting for the following not available instruments has not been verified: X111 (light glass); X101 (sampling device). | Components to be provided and fitting to be verified. / X111 installed. For the Novaseptum refer to NC-11009 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Welds indication on isomentric not correct for the following iso: PC/D B205-3; PC/D B205-4; PC/D B205-5. | Iso updated to be verified | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Datasheet P16-0052-SP-10 MANWAY rev 1.2: wrong model type indicated on the datasheet (number of lid clamps wrong: 8 instead of 6 indicated on datasheet) | Datasheet to be updated Fabiana Cortellini 01-MAR-2018. The datasheet has been updated in rev 1.3 and checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Datasheet P16-0052-SP-65 BURST DISK Y811 rev 1.2: name of supplier and model to be correct. | Datasheet to be updated. Fabiana Cortellini 05-FEB-2018: Datasheet has been updated in rev 1.3 and checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Datasheet P16-0052-SP-61 LEVEL SWITCH L111 rev 1.1: tag reference not complete; wrong tag number. | Datasheet to be updated. Fabiana Cortellini 01-MAR-2018: refer to B155 item number 2975. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Datasheet P16-0052-SP-90 TEMPERATURE INDICATOR T101 1.1: wrong transmitter model indicated on the label, but type of transmitter ok. | Wrong label to be exchanged Fabiana Cortellini 04-APR-2018: Label exchanged and checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | the following datasheets have not been checked because istruments/equipment/information not available: P16-0052-SP-13 lightglass; P16-0052-SP-14-2 sampling port. | Datasheet to be checked. / All the components are installed according to the datasheets. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Test Log: sprayball not tagged. | Put the correct tag on the sprayball tube (visible from the outside of the tank). / All the tank nozzles have been installed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | the following Instrument are not tagged: P101, P102, L111, Y811, X111, X101, G811. | Instrument to be tagged. / All the instrument are tagged permanently | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | for the following ISO not all welds have been done: PC/D B205-3; PC/D B205-4; PC/D B205-5. | Welds to be done. / All the ISOs listed are completely welded. All the welds are indicated on the ISO and reported on the welding book. Information collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Vessel drawing is not in 'As built' revision | As built' revision to be included in the DOE by BLF Fabiana Cortellini 03-APR-2018: construction drawing has been issued by BLF in rev 2.1, checked and approved with "no comment". | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | User Manual is not available | To be included in the VTOD Seun Idowu 02-AUG-2018: User Manual available, checked and included in VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Manufacturer's name plate is not available in the DOE | Manufacturer's name plate to be included in the VTOD Seun Idowu 22-MAR-2018: Manufacturer’s name plate document checked and included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Insulation documents are not available | Insulation documents to be included in the VTOD. / Novartis decided to insulate the skid on site. Responsibility of a different vendor. No doc to be added into the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #6 : Ht Nb 521867 instead of 0521867 | Update the Material Cert. List Seun Idowu 22-MAR-2018: Material cert. list updated. Heat number amended on the material cert. list. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #11 + 14 : Drawing Nb PC201 instead of PC155 | Update the Material Cert. List Seun Idowu 22-MAR-2018: Material cert. list updated. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #N81 : Error on the Cert. Nb. | Update the Material Cert. List Seun Idowu 22-MAR-2018: Material cert. list updated. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #N2, N4 and N5 : Material certificates not available. | Add the mising certificates and update the Material Cert. List Seun Idowu 22-MAR-2018: Manufacturer document for the manway included in the VTOD. Material cert. list updated (N14) | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Filler metal (1733) - Grade incomplete | Write ''T 19 9 LR C1/M21 3'' on the Materiel Cert. List Seun Idowu 02-AUG-2018: Material certificate list updated. Grade T 19 9 LR C1/M21 3 written on material certificate list. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #2 : 2 Different Ht Nb. on the Material Cert. | One Ht Nb shall be used. Check the Material Cert. and update the Material Cert. List Seun Idowu 02-AUG-2018: NC-0673 entry error therefore, there is no non-conformance for this punch item. Material certificate list does not need to be updated since two different heat numbers are required. Material certificates for these heat numbers are available, checked and included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #N56 and N57 are missing | Add Material Cert. in the VTOD and up date the Material Cert. List Seun Idowu 23-MAR-2018: Material cert. included in the VTOD. Material cert. list updated. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Material certificate of gaskets are missing: referred only to the manhole gasket | Gaskets documents to be included in the VTOD Seun Idowu 02-AUG-2018: Material certificates for the gaskets including manhole gasket are available, checked and included in VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Spray ball and diptubes documents are missing | Spray balls and diptubes documents to be included in the VTOD Seun Idowu 31-JUL-2018: Spray balls and diptubes documents included in VTOD. Refer to B205 skid SAT protocol, section piping certificate material. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Welds 108 to 143 - Reference to the WPS D53 is missing. | Update the Welding Log Seun Idowu 23-MAR-2018: Welding log updated. WPS D53 documented on the welding log. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Welding Map - Welds 147 to 150 and 405B are missing | Update the Welding Log or the Welding Map Seun Idowu 23-MAR-2018: Welding map updated. Welds 147 to 150 and 405B included on the welding map. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Welds 307 to 308 - WPS D68-1 is missing | Up date the Welding Log Seun Idowu 23-MAR-2018: WPS D68-1 document included in the welding book and VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Welding Log - Welds 407A to 409F - WPS Nb ''EN -8-2-FW-FF-MU-100'' instead of ''EN -8-2-FW-FF-MU-101'' | Up date the Welding Log or the Welding Log Seun Idowu 23-MAR-2018: Welding log updated. Welds 407A to 409F - WPS Nb checked and updated. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Accessory welding documents are missing | Accessory welding documents to be included in the DOE by BLF Seun Idowu 31-JUL-2018: Accessory welding documents included in VTOD. Refer to B205 skid SAT protocol, section piping welding report. See prolog number 11274. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Flushing / drying procedure and certificates are missing | Flushing and drying certificate to be included in the DOE by BLF/ Flushing is included in the passivation procedure. Drying executed at FAT but not documented. Accepted by NVS (Zanobini email 25aug2018). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | 2nd Jacket side hydrostatic test is missing | Last hydraustatic test jacket side to be included in the DOE by BLF Seun Idowu 23-MAR-2018: Second Jacket side hydrostatic test included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Notified Body's attestation is missing. This Item is not blocking for the MC; it will be conditionally accepted by the Commissioning team. | Notified Body's attestation to be included in the VTOD Seun Idowu 02-AUG-2018: Certificate of conformity (notified body attestation document) available, checked and included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Notified Body's design examination is missing | Notified Body's examination design to be included in the DOE by BLF Seun Idowu 23-MAR-2018: Notified body (TUVRheinland) test report - examination of design included in the VTOD | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Maintenance log is missing | Maintenance log to be included in the DOE by BLF Seun Idowu 02-AUG-2018: Maintenance log available, checked and included in VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Calculation Notes - PED 97/23/CE instead of 2014/68/CE and MAWT = 10°C instead of 0°C | Update Calculation Notes Seun Idowu 27-MAR-2018: Calculation note updated. 2014/68/CE and MAWT of 0°C documented on the calculation note. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Test drainability not performed acccording to the family approach agreed (test performed on B217) | Test to be performed during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Level strapping not performed acccording to the family approach agreed (test performed on B217) | Test to be performed during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Sprayball coverage test not performed acccording to the family approach agreed (test performed on B217) | Test to be performed during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Name plate has been checked and value for pressure test for the jacket is not in accordance with the construction drawings. | Construnstruction drawing to be updated by BLF. Fabiana Cortellini 03-APR-2018: construction drawing has been issued by BLF in rev 2.1, checked and approved with "no comment". | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | The sightglass installed on the manway had wrong size (too small): it has been changed according to the tank construction drawing and re-installed. | Pressure test to be re-executed for the manway. / Pressure test executed on the manway according to the required value of design pressure. Documentation collected into the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Leak pressure test not performed | Test to be performed during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Tank not completely clean after electropolishing and passivation (issues during sprayball coverage test performed on B217). | Complete degreasing / cleaning of the tank to be performed on site RCAR 11jul2018: this punch to keep in mind the action of the degreasing in case of fail of sprayball coverage test. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | All components are installed without tag (plastic label) according to NVS standard for tagging (refer P&ID FAT Protocol attachment 30 to test 4.1.1) | PG to install tags (plastic label) according to NVS standard for tagging on all compnents according to FAT Protocol attachment 30 to test 4.1.1 ccia 03-mar-2018: tags check done also during SAT. for list of missing tags refer R118_PSAT AT1 and AT12 (ref attached file) CCIA 06-Jun-2018: tagging has been completed and where tags are missing temporary tags have been installed. Criticality reduced to B GCO: 21-Aug-2018: Tagging done By PG | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Line -002 between flexible X503 and nozzle N006 is not installed (including components X503 and V503 and fittings) (Line out of the skid, manufature not possible before installation on site) | PG to install the line with fittings and components missing on site CCIA 03-mar-2018: checked during sAT. refer R118_PSAT AT1. line installed according to P&ID | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Line -003 between nozzle N013 and RG/S1-BL002 is not installed including components and fittings (Line out of the skid, manufature not possible before installation on site) | PG to install the line with fittings and components missing on site CCIA 03-mar-2018: checked during SAT. refer R118_PSAT AT1. Line installed according to P&ID | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Line -001 between nozzle N8 and valve V004 is not installed including components and fittings (Line out of the skid, manufature not possible before installation on site) | PG to install the line with fittings and components missing on site CCIA 03-mar-2018: checked during SAT. refer R118_PSAT AT1. Line installed according to P&ID | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Lines -012 and -013 ERF/ERFR Jacket inlet and outlet are not installed including components and fittings (Line out of the skid, manufature not possible before installation on site)) | PG to install the line with fittings and components missing on site CCIA 03-mar-2018: checked during SAT. refer R118_PSAT AT1. Line installed according to P&ID | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Lines -042 and -013 (CIP) below the platform are not installed including components and fittings (Line out of the skid, manufature not possible before installation on site) | PG to install the line with fittings and components missing on site CCIA 03-mar-2018: checked during SAT. refer R118_PSAT AT1. Line installed according to P&ID | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Line -035 is not installed in the drain collection (Line out of the skid, manufature not possible before installation on site) | PG to install the line on site CCIA 03-mar-2018: checked during SAT. refer R118_PSAT AT1. Line installed according to P&ID | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Line -026 (EPIF) crossing the platform is not installed (Line out of the skid, manufature not possible before installation on site) | PG to install the line on site CCIA 03-mar-2018: checked during SAT. refer R118_PSAT AT1. Line installed according to P&ID | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Lines -074, -075, -076, -077 including components and fittings are not installed (Line out of the skid, manufature not possible before installation on site) | PG to install the lines with fittings and components missing CCIA 05-mar-2018: with reference to the SAT protocol (P&ID and isometric tests) the lines have been installed and checked | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | PG isometric drawings are stuctured in the way that one drawing is collecting more than one line number. Each isometric includes all the data mentioned in the P&ID (i.e. line numbers, iso breaks, piping class limits, battery limits, etc.) | PG to create a cross reference table line number/isometric drawing. CCIA 26-feb-2018: the document has been correctly provided. Refer attached files. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.001 Page 16 Main Switch Label missing on drawing. | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.001 Page 16 Wiring diagram has some unlegible dimenssions (Autocal Printing Issue) | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.001 Page 16 Vertical Dimensions for Emergency Button and Main Switches are not correct: Design says 1000mm value is 1018mm and Design says 500mm and is 582mm | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.001 Page 17 Wiring diagram has some unlegible dimenssions (Autocal Printing Issue) | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.001 Page 17 Layout of devices is not as per installation: Many Terminal strips are missing, Location of devices is not correct, Grounding and Shielding bars are not all represented nor labelled, The Cablofil in the bottom is not | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.001 Page 18 Routing does not show lower cablofil | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.001 Page 19 Compression Fitting installed at top of cabinet is not shown. | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.001 Page 20 Not all Grounding and Shielding bars are shown. Earthing and Shielding inteonnections are not reflecting the actual wiring. | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.001 Page 21 Not all Grounding and Shielding bars are shown. Earthing and Shielding inteonnections are not reflecting the actual wiring. | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.001 Page 260 Pneumatic Distribution not represented as installed and labeled: - 260D1 and 260D2 have Eight ports. - Manual Valves not represented - Spare Ports not represented | Update Drawing and Label the internal Pneumatic Distribution | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Some correction have been raised on the P&ID (refer P&ID FAT Protocol attachment 30 to test 4.1.1) | R118 P&ID to be updated according to the remarks in the FAT Master copy (refer P&ID FAT Protocol attachment 30 to test 4.1.1) CCIA 09-feb-2018: the comments have been implemented on master P&ID on 02-feb-2018. Novartis to update the P&ID in Comos. The point is transferred to Novartis. CCIA 03-mar-2018: P&ID to be updated also according comments in R118_PSAT AT1 CCIA 03-JUL-2018: all the comments from SAT and MCWDII have been transferred to Master P&ID | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | With reference to the lines not installed during the FAT, the P&ID walkdown cannot be considered complete | P&ID walkdown to be completed for the lines not installed at the FAT CCIA 09-feb-2017: SAT protocol has been approved and it is formalized to complete the check for parts not checked during FAT. This point is closed with the SAT execution. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Instrument Calibrations / Hart Data: All verified vendor calibration certificates (except for flowmeters that certify required measuring range) show only standard manufacturer calibration. (Example: All Temperature transmitters are calibrated 0 to 150°C where Data Sheet says 0 to 140°C.) | It is Pierre Guerin’s responsibility to deliver the equipment with all instrument set-up with the correct measuring range as per Instrument Data Sheet (which is as per URS). Pierre Guerin should set-up all instruments prior to site testing. During Set-up Pierre Guerin should note / document all hart parameters. Calibration and re-configuration report with calibration ranges to be issued by PG. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | EC conformity declaration of the whole system delivered by PG is missing | PG to provide the EC conformity declaration of the whole system | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Pictures of boroscopic inspection according to PSP008 are missing even the bosroscopic incpection has been correctly performed | Welding inspector to provide the missing pictures | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Documentation check of Operating file for system R118 has not been performed by the document checker | Documentation check of Operating file for system R118 to be performed by the document checker CCIA 07-dec-2017: documents provided and checked | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Documentation check of Mechanical Maintenance file for system R118 has not been performed by the document checker | Documentation check of Mechanical Maintenance file for system R118 to be performed by the document checker CCIA 17-JAN-2018: documents provided and checked | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Documentation check of Electrical Maintenance file for system R118 has not been performed by the document checker | Documentation check of Electrical Maintenance file for system R118 to be performed by the document checker CCIA 17-JAN-2018: documents provided and checked | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Documentation check according to PG LOD (List of Documentation), contractual VDR and Novartis VTOD chapter for system R118 has not been performed by the document checker | Documentation check according to PG LOD (List of Documentation), contractual VDR and Novartis VTOD chapter for system R118 to be performed by the document checker | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Some corrections have been raised on the datasheets (refer Set of datasheets FAT Protocol attachment 40 to test 4.1.1) | Set of datasheets to be updated according to comments (refer Set of datasheets FAT Protocol attachment 40 to test 4.1.1) CCIA 22-dec-2017: set of datasheets has been updated by PG. ref attached set | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | PED documentation check has not been executed by the welding inspector during FAT | Welding Inspector to perform PED documentation check CCIA / Hilfiger - 18-JAN-2018: after meeting in Niort (Pierre Guerin) the point is closed (ref. attached file) | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Welding Inspector specific VTOD chapter documentation check has not been executed during FAT | Welding Inspector to perform specific VTOD chapter documentation check CCIA / Hilfiger - 18-JAN-2018: after meeting in Niort (Pierre Guerin) the point is closed (ref. attached file) | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | New measurement of the resistance between main earth bar and different segments of cable conduits will be needed on site | PG to re-perform on site measurement of the resistance between main earth bar and different segments of cable conduits CCIA 13-apr-2018: a measurement has been performed and the resistance between the main cable tray and the last piece of the conduit is 0.4ohm | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.001 General Dual Source Cabinet | Add a Label: White Text/Red Background Attention cette armoire est allimentée par deux sources CCIA 01-feb-2018: label correctly installed | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 General Dual Source Cabinet | Add a Label: White Text/Red Background Attention cette armoire est allimentée par deux sources | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 16 Main Switch Label missing on drawing. | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 16 Wiring diagram has some unlegible dimenssions (Autocal Printing Issue) | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 17 Wiring diagram has some unlegible dimensions (Autocal Printing Issue) | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 17 Layout of devices is not as per electrical drawing (installed cabinet layout is acceptable, drawing to be updated): Many Terminal strips are missing, Location of devices is not correct, Grounding and Shielding bars are | Update Drawing, Install missing Labels after the update of the drawing CCIA - AZwi: drawing updated and labels installed | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 18 Routing does not show lower cablofil | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 19 Compression Fitting installed at top of cabinet is not shown. | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 20 Not all Grounding and Shielding bars are shown. Earthing and Shielding interconnections are not reflecting the actual wiring. | Update Drawing Show all the copper bars, their interconnections and wiring as per attachment to the wiring diagram | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 21 Not all Grounding and Shielding bars are shown. Earthing and Shielding interconnections are not reflecting the actual wiring. | Update Drawing Show all the copper bars, their interconnections and wiring as per attachment to the wiring diagram | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 60 Some wire Labels are wrong in diagram | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 80 Some wire Labels are wrong in diagram | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 81 Some wire Labels are wrong in diagram | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 100 ET200 Addressing is wrong | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 101 ET200 Addressing is wrong | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 126 Some labels unlegible on wiring diagram | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 260 Pneumatic Distribution to be update, wrong tags, valves and spare not indicated | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 224 Pneumatic Distribution to be update, wrong tags, valves and spare not indicated | Electrical drawing to be updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 Page 260 Pneumatic Distribution not reprented as installed and labeled: - 260D1 and 260D2 have Eight ports. - Manual Valves not represented - Spare Ports not represented | Update Drawing and Label the internal Pneumatic Distribution CCIA - AZwi: labels installed and drawing updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | All components are installed without tag (plastic label) according to NVS standard for tagging | PG to install tags (plastic label) according to NVS standard for tagging on all compnents CCIA 03-mar-2018: tag check has been executed also during SAT. tags missing are listed in R152_PSAT AT2 and AT12 (ref attached file) CCIA 25-apr-2018: temporary tagging has been installed. Criticality decreased to B GCO 21-aug-2018: Tagging done by PG. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Valve V503 missing | PG to install the component and the line on site (it is linked to the vessel) CCIA 03-mar-2018: refer R152_PSAT AT2. valve present, installed and tagged | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Some correction have been raised on the P&ID (refer P&ID FAT Protocol attachment 35 to test 4.1.1) | R152 P&ID to be updated according to the remarks in the FAT Master copy (refer P&ID FAT Protocol attachment 35 to test 4.1.1) CCIA 09-feb-2018: the comments have been implemented on master P&ID on 02-feb-2018. Novartis to update the P&ID in Comos. The point is transferred to Novartis. C. Fallet 02.Feb.2018: PID update is required prior to qualification only. Recategorized as cat. B. CCIA 03-mar-2018: PID to be updated also according to comments on R152_PSAT AT2 CCIA 03-JUL-2018: all the comments from SAT and MCWDII have been transferred to Master P&ID | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | PG isometric drawings are stuctured in the way that one drawing is collecting more than one line number. Each isometric includes all the data mentioned in the P&ID (i.e. line numbers, iso breaks, piping class limits, battery limits, etc.) | PG to create a cross reference table line number/isometric drawing. CCIA 26-feb-2018: the document has been correctly provided. Refer attached files. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | The following lines were not installed during the FAT P&ID walkdown (manufature not possible before installation on site): -004, -060, -001, -015, -016, -034, -003, -119 | PG to install the lines and the components on site CCIA 03-mar-2018: refer R152_PSAT AT2 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Pump -P2 not installed | PG to install the component CCIA 03-mar-2018: pump present on the platform. ref. R152_PSAT AT2 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | With reference to the lines not installed during the FAT, the P&ID walkdown cannot be considered complete | P&ID walkdown to be completed for the lines not installed at the FAT CCIA 09-feb-2017: SAT protocol has been approved and it is formalized to complete the check for parts not checked during FAT. This point is closed with the SAT execution. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Instrument Calibrations / Hart Data: All verified vendor calibration certificates (except for flowmeters that certify required measuring range) show only standard manufacturer calibration. (Example: All Temperature transmitters are calibrated 0 to 150°C where Data Sheet says 0 to 140°C.) | It is Pierre Guerin’s responsibility to deliver the equipment with all instrument set-up with the correct measuring range as per Instrument Data Sheet (which is as per URS). Pierre Guerin should set-up all instruments prior to site testing. During Set-up Pierre Guerin should note / document all hart parameters. Calibration and re-configuration report with calibration ranges to be issued by PG. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Material certificate missing for swagelok fittings (elbows, T-pieces) in piping class EG18X40 of isometric 232805 | PG to provide the certificate CCIA 18-JAN-2018: missing certificates have been provided and checked. Refer attached index of traceability updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | EC conformity declaration of the whole system delivered by PG is missing | PG to provide the EC conformity declaration of the whole system | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Pictures of boroscopic inspection according to PSP008 are missing even the bosroscopic incpection has been correctly performed | Welding inspector to provide the missing pictures | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Documentation check of Operating file for system R152 has not been performed by the document checker | Documentation check of Operating file for system R152 to be performed by the document checker CCIA 07-dec-2017: documents provided and checked | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Documentation check of Mechanical Maintenance file for system R152 has not been performed by the document checker | Documentation check of Mechanical Maintenance file for system R152 to be performed by the document checker CCIA 17-JAN-2018: documents provided and checked | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Documentation check of Electrical Maintenance file for system R152 has not been performed by the document checker | Documentation check of Electrical Maintenance file for system R152 to be performed by the document checker CCIA 17-JAN-2018: documents provided and checked | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Documentation check according to PG LOD (List of Documentation), contractual VDR and Novartis VTOD chapter for system R152 has not been performed by the document checker | Documentation check according to PG LOD (List of Documentation), contractual VDR and Novartis VTOD chapter for system R152 to be performed by the document checker | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Passivation certificate missing for the following pieces: dwg #232802 page 2/6 dwg #232802 page 3/6 dwg #232805 page 2/3 | PG to provide the missing passivation certificates | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Some corrections have been raised on the datasheets (refer Set of datasheets FAT Protocol attachment 45 to test 4.1.1) | Set of datasheets to be updated according to comments (refer Set of datasheets FAT Protocol attachment 45 to test 4.1.1) CCIA 13-feb-2018: datasheets have been updated according to the comments. ref attached closure evidence | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | PED documentation check has not been executed by the welding inspector during FAT (particular attention to be paid for filter housings) | Welding Inspector to perform PED documentation check (particular attention to be paid for filter housings) CCIA / Hilfiger - 18-JAN-2018: after meeting in Niort (Pierre Guerin) the point is closed (ref. attached file) | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Welding Inspector specific VTOD chapter documentation check has not been executed during FAT | Welding Inspector to perform specific VTOD chapter documentation check CCIA / Hilfiger - 18-JAN-2018: after meeting in Niort (Pierre Guerin) the point is closed (ref. attached file) | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | New measurement of the resistance between main earth bar and different segments of cable conduits will be needed on site | PG to re-perform on site measurement of the resistance between main earth bar and different segments of cable conduits CCIA 13-apr-2018: a measurement has been performed and the resistance between the main cable tray and the last piece of the conduit is 0.4ohm | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.001 General No Manufactuer Label on the cabinet / CE Marking | Provide Manufacturer Label inside Cabinet - Manuafactuer Name - Manufacturer Address - Year of built - Order Number CCIA 01-feb-2018: label correctly installed | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Cabinet 341.2.64/J.003 General No Manufactuer Label on the cabinet / CE Marking | Provide Manufacturer Label inside Cabinet - Manuafactuer Name - Manufacturer Address - Year of built - Order Number CCIA 01-feb-2018: label correctly installed | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Conduits Grounding: A resistance measurement between main earth bar and different segments of cable conduits show up a relative high impedance This could be refused by notified body because not in accordance with Low Voltage Directive C15-100 | PG to propose a working and suitable design according to regulations PG to install groundig connector as much as possible prior to delivery. Remaining to be done on site. CCIA 13-apr-2018: cable conduit installation has been completed according to the agreed technical solution | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Conduits Grounding: A resistance measurement between main earth bar and different segments of cable conduits show up a relative high impedance This could be refused by notified body because not in accordance with Low Voltage Directive C15-100 | PG to propose a working and suitable design according to regulations PG to install groundign connector as much as possible prior to delivery. Remaining to be done on site. CCIA 13-apr-2018: cable conduit installation has been completed according to the agreed technical solution | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Studs (goujon) too shorts on some nozzles | BLF to check and exchange them on site / All the studs have been changed with longer ones. All the nozzles have been cleaned before the installation of instrument/sprayballs/dip tube. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Load cells not installed, no check done | load cells to be installed on site. / Load cell installed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Sprayball on nozzle N39 missing | To be provided by BLF / Sprayball installed and checked according to the ISO. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Tolerance on diameter of ingold plugs not checked because final components not installed (sampling, conductivity, ..) | Test to be checked during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Degree of ingold port not aligned for the nozzle: N79 (spare). | Measured value (rounded down to full degrees) needs to be indicated on the vessel/GA drawing with a note “measured at FAT”. • N79: spare nozzle: not critical. Fabiana Cortellini 03-APR-2018: construction drawing has been issued by BLF in rev 2.1, checked and approved with "no comment". | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | The following components are available but not installed: P101 - L111 - P102 - P103 - Y811. | Components to be installed on site, after tank installation. / All the components are installed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | The following components are not available: W101 - X111 - G811 - X101 - manway sight glass | Components to be provided and installed./ All the components are installed. For the Novaseptum refer to NC-11010. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | All tank nozzles, Valves and outlet line are not tagged. | Final tags to be put in place on site, after tank installation. / RCAR 02JUL2018: all the valves are temporary or permanently tagged; nozzles tag is on going; labeling will be done after insulation, as agreed (not critical). / RCAR 22aug2018: nozzles tags installed; permanently tags installed. Labeling not in the scope of BLF1. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | weldings information (heat number and certificate number) missing on the isometrics. | Information to be filled in after completion of weldings. / All the ISOs have been completed with the heat numbers (a dedicated table is attached to the specific ISO - when it's required). All the welds number is recorded on the last ISO revision. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Fitting for the following not available instruments has not been verified: X111 (light glass); X101 (sampling device). | Components to be provided and fitting to be verified. / Light glass installed; for the Novaseptum refer to NC-11010. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Line number on Iso not conformed with line nomber on P&ID: 50-BUFFER-EG16N40-B206-072 instead of 50-BUFFER-EG16N40-B206-056. | P&ID to be updated accordingly. Line 50-CIP-EG16N40-B204-O89: missing a flange on the P&ID. / Refer to NC-0867 for the closure. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Welds indication on isomentric not correct for the following iso: PC/D B206-3; PC/D B206-4; PC/D B206-5. | Iso updated to be verified | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Datasheet P16-0052-SP-10 MANWAY rev 1.2: wrong model type indicated on the datasheet (number of lid clamps wrong: 8 instead of 6 indicated on datasheet) | Datasheet to be updated Fabiana Cortellini 01-MAR-2018. The datasheet has been updated in rev 1.3 and checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Datasheet P16-0052-SP-65 BURST DISK Y811 rev 1.2: name of supplier and model to be correct. | Datasheet to be updated. Fabiana Cortellini 05-FEB-2018: Datasheet has been updated in rev 1.3 and checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Datasheet P16-0052-SP-61 LEVEL SWITCH L111 rev 1.1: tag reference not complete; wrong tag number. | Datasheet to be updated. Fabiana Cortellini 01-MAR-2018: refer to B155 item number 2975. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Datasheet P16-0052-SP-90 TEMPERATURE INDICATOR T101 1.1: wrong transmitter model indicated on the label, but type of transmitter ok. | Wrong label to be exchanged Fabiana Cortellini 04-APR-2018: Label exchanged and checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Test Log: sprayball not tagged. | Put the correct tag on the sprayball tube (visible from the outside of the tank). / Sprayballs has been tagged on site. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | the following Instrument are not tagged: P101, P102, L111, Y811, X111, X101, G811. | Instrument to be tagged. / All the instrument have permanently tagged. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | for the following ISO not all welds have been done: PC/D B206-3; PC/D B206-4; PC/D B206-5 | Welds to be done. / All the ISOs listed are completely welded. All the welds are indicated on the ISO and reported on the welding book. Information collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Vessel drawing is not in 'As built' revision | As built' revision to be included in the DOE by BLF Fabiana Cortellini 03-APR-2018: construction drawing has been issued by BLF in rev 2.1, checked and approved with "no comment". | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Calculation Note - Design temp. = 10/160°C instead of 0/160°C PED 97/23/CE instead of 2014/68/CE This point is not blocking the MC. It's conditionally accepted by the management/ C&Q team. | Change the minimum design temperature and the PED, then issue a new revision Mario Luiso 11-SEP-2018:The minimum design temperature has been changed and the right law name 2014/68/CE is written in VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Insulation documents are not available | Insulation documents to be included in the VTOD. / Novartis decided to insulate the skid on site. Responsibility of a different vendor. No doc to be added into the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #N56 and N57 are missing | Add Material Cert. In the VTOD and up date the Material Cert. List Mario Luiso 11-SEP-2018: Material Cert. is added In the VTOD and the Material Cert. List is updated correctly | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Material certificate of gaskets are missing: related to the manhole gasket only. | Gaskets documents to be included in the VTOD / material certificate for the gasket manhole is included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Spray ball and diptubes documents are missing | Spray balls and diptubes documents to be included in the VTOD Seun Idowu 31-JUL-2018: Spray balls and diptubes documents included in VTOD. Refer to B206 skid SAT protocol, section piping certificate material. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Welds 151 to 154 and 309 to 312 doesn't appear on the Welding Map | Up date the Welding Map Mario Luiso 12-SEP-2018: Welding log and welding map are updated correctly and weld 152 to 154 and 309 to 312 don't exist | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Welds 406 - Welder, Ht Nb and date are missing. | Up date the Welding Log Mario Luiso 12-SEP-2018: Welding log and welding map are updated correctly and weld 406 doesn't exist | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Accessory welding documents are missing | Accessory welding documents to be included in the DOE by BLF Seun Idowu 15-MAY-2018: Accessory welding documents included in VTOD. Refer to B206 skid SAT protocol, section piping welding report. See prolog number 11306. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Flushing / drying procedure and certificates are missing | Flushing and drying certificate to be included in the DOE by BLF/ Flushing is included in the passivation procedure. Drying executed at FAT but not documented. Accepted by NVS (Zanobini email 25aug2018). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Notified Body's attestation is missing. This Item is not blocking for the MC; it will be conditionally accepted by the Commissioning team. | Notified Body's attestation to be included in the VTOD Mario Luiso 11-SEP-2018: Notified Body's attestation is included in the VTOD | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Notified Body's design examination is missing This point is not blocking the MC. It's conditionally accepted by the management/ C&Q team. | Notified Body's examination design to be included in the DOE by BLF Mario Luiso 11-SEP-2018: Notified Body's examination design is included in the DOE by BLF | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Maintenance log is missing | Maintenance log to be included in the DOE by Novartis Mario Luiso 12-SEP-2018: Maintenance log added in VTOD | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Diptube not dimensionally checked. | To be checked before mechanical completion / dip tube checked according to the ISO. document collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Test drainability not performed acccording to the family approach agreed (test performed on B217) | Test to be performed during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Level strapping not performed acccording to the family approach agreed (test performed on B217) | Test to be performed during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Sprayball coverage test not performed acccording to the family approach agreed (test performed on B217) | Test to be performed during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | The sightglass installed on the manway had wrong size (too small): it has been changed according to the tank construction drawing and re-installed. | Pressure test to be re-executed for the manway. / Pressure test executed on the manway according to the required value of design pressure. Documentation collected into the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Leak pressure test not performed | Test to be performed during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Tank not completely clean after electropolishing and passivation (issues during sprayball coverage test performed on B217). | Complete degreasing / cleaning of the tank to be performed on site RCAR 11jul2018: this punch to keep in mind the action of the degreasing in case of fail of sprayball coverage test. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 05, 16: hardware devices description in the wiring diagrams hardware list does not match with the installed hardware | wiring diagrams hardware list to be corrected MCHR 16-MAR-2018: Wiring diagrams corrected | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 06: missing or wrong cable labels on the terminals inside control cabinet. | terminals labels to be put on the wires / Labels have been added to all the terminals | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 08, 14: some labels in the control cabinet are not correct (wrong description/wrong colors). | labels to be corrected / MCHR 06-JUL-2018: Labels have replaced (double alimentation, labels for UPS powered devices) | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 01: hardware documentation of electrical components of the cabinet is missing | hardware documentation to be provided and checked M.POZZI 13-MAR-2018: Hardware documentation provided | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: cabinet manufacturer's self-check sheet is missing | Whole cabinet builder test incl. declaration of conformity to be provided. MCHR 20-MAR-2018: Certificate provided for self-checks. CE certificate must be reissued with proper norms and titles. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 03: cabinet CE certificate is missing | certificate to be provided and checked MCHR 16-MAR-2018: certificate provided from SPIE | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 01: MCB after redundant 24V supply module shall be different type and not Schneider (rate is not correct) | Siemens type 5SY4220-5 to be provided and installed MCHR 19-MAR-2018: Cabinet submitted to notified body review. Result is that MCB shall be changed with Siemens type. MCB already replaced in cabinet, wiring diagrams updated | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: vent device with filter is to be installed on the cabinet to prevent overpressure in case of air leak on pneumatic circuit inside the cabinet | vent device with filter to be provided and installed M.CHRAPPAN 13-MAR-2018: Vent device installed | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 05: earthing of the skid: wiring of the earthing cable/cords on the skid is completely missing | Not compliant with Low Voltage Directive C15-100. Eearthing of the skid to be done and checked Preparing the skid for earthing must be finished at vendor site including measurement. MPOZZI 12-MAR-2018: Cord from Skid to Building earth provided | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 11: some cabling on instrument have been bent too much, this will damage the cable in a short time | cables to be adjusted properly on the skid / MCHR 10-JUL-2018: no issues detected on the skid | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 08: PROFIBUS cable numbering is not as per Novartis procedure | wiring diagrams to be corrected, labels on cables to be done. / Clemessy will label the profibus cables. Wiring diagram will be updated accordingly and the verification will be done during SAT. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 10, 14: cable colors for 24V: brown is + white is - as per colour code: some cables on wiring diagram are inverted | wiring diagrams to be corrected, cabling in the cabinet to be inverted. / Wiring diagram updated accordingly. Document collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 01: instrument list not available; the test has been executed with the P&Ids as a reference document | instrument list to be provided and checked VS the P&ID M.POZZI 12-MAR-2018: Document provided, it has to be issued formally to JACOBS (missing doc. number, revision, vendor info) MCHR 28-AUG-2018: List has been provided for SAT | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: instruments missing: bursting disk | instrument to be installed on skid and connected to control cabinet M.CHRAPPAN 13-MAR-2018: Instrument installed and connected to control cabinet. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: TT101 (tank bottom temp): the wrong instruments type is installed (TR15 non aseptic instead of TM411 aseptic) | Correct type of transmitter is installed, only label must to be exchanged. M.POZZI 12-MAR-2018: Label exchanged. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | instrument configuration sheets are not available; the test cannot be executed | instrument configuration sheets to be provided and test to be executed / MCHR 06-JUL-2018: Configuration sheets are provided in rev. 0.1 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital output (on/off valves) loop check failure: V002 not on the skid (loose valves will be installed at site) | test to be done on site / MCHR 09MAY2018: IO test performed in SAT Test TD03.4.01 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 14: some wires are missing (field device not wired - V001, V002, V922, V930, V963, V992, air supply - earth wire missing on XRINT.02) | cable to be layed down and connected to cabinet M.CHRAPPAN 09-MAR-2018: V001 connected, rilsan pipes for V922, V930, V963, V992 already pulled but not yet connected because actuators are not mounted. air supply is present Clemessy to install loto valves on V930, V963, V992 M.CHRAPPAN 19-APR-2018: Installation completed for all the points mentioned above | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 14: load cells are not installed under the tank, the wires are not layed down to the cabinet, the cable ways are not present on the skid | to lay down the cables and the cable ways (M.Pozzi 07-MAR-2018): load cells installed | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 06. wrong colour of terminal indicated on wiring diagram | wiring diagram to be corrected M.Pozzi 07-MAR-2018: wiring diagrams corrected, master copy with redmarks inside cabinet | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital input loop check failure: GSH-811 rupture disk: disk not installed | rupture disk and indicator to be installed and connected, test to be redone / MCHR 19MAR2018: Rupture disk and sensor are connected. Dynamic tests to be performed during commissioning / MCHR 09MAY2018: IO test performed in SAT Test TD03.4.01 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital output (on/off valves) loop check failure: V954, V961, V003, V004 valves not installed | valves to be installed and wired: test to be repeated / RCAR 11jul2018: valves installed and wired on site. Test to be performed. / / MCHR 09MAY2018: IO test performed in SAT Test TD03.4.01 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital output (on/off valves) loop check failure: V401, not possible to command it | test to be done on site / MCHR 09MAY2018: IO test performed in SAT Test TD03.4.01 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital output (on/off valves) loop check failure: V701, pneumatic connetion on the valve is wrong | pneumatic connection on the valve to be fixed / / MCHR 09MAY2018: IO test performed in SAT Test TD03.4.01 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital output (on/off valves) loop check failure: V502, wrong connction on FESTO block | connection on FESTO block to be fixed / MCHR 09MAY2018: IO test performed in SAT Test TD03.4.01 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: digital output (on/off valves) loop check failure: V001, V922, V930, V963, V992 are loose valves | test to be done on site / MPO - 02aug2018: valves have been installed and connected see Clemessy CTOD Sec. 12.4 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 03: analogue input loop check failure: TT982, TT980: RM042 transducer in the cabinet not configured | transducer to be configured / MCHR 10-JUL-2018: Device report for TT982, TT980 attached to SAT. IO check was done by NVS with no issues. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 04: analogue output (control valve) loop check failure: R701: valve actuator seems not properly configured | valve actuator to be configured / MCHR 09MAY2018: IO test performed in SAT Test TD03.4.01 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 03: analogue input loop check failure: W101: weighing cells not installed and not wired | weighing cells will be installed and wired at site; test to be done on site / MCHR 09MAY2018: IO test performed in SAT Test TD03.4.01 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | cabinet is not clean, lot of construction material is around | cleanliness of cabinet to be checked on site Tuesday 27-MAR-2018: Cabinet has been cleaned by SPIE | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: missing information on the CE label: max Icc that the cabinet can sustain. A second label with the client data is missing | labels to be corrected/added M.Pozzi 07-MAR-2018: Label with max Icc provided XQUA 04-JUL-2018: All the labels are present and conform | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 09: poor fixing of part of the piping/cable trays supports on the top of the buffer storage tanks | supports to be analysed and in case reinforced. / Support installed on the ceiling of the room to properly fix the frame. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 11: due to the works in progress it is not possible to check cable trays completness, clashes and interference, holes and openings | checks to be done when construction activities are completed / MCHR 06-JUL-2018: Cable trays are complete | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 12: some rilsan pipes are touching CIP pipes - near valve V952 T980 cable is touching the steam pipe. | rilsan pipes to be repositioned / MCHR 23-AUG-2018: Rilsan is ok | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | this test refers to the check of the calibration of instruments, it is not foreseen during FAT | test to be done on site | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | n° 02: the profibus address of Festo block is wrong | wiring diagram to be corrected with the Profibus address indicated in the I/O list and micro swith configuration on device to be changed. MCHR 10-JUL-2018: Profibus address is corrected on I/O list and Switch configuration | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | LOTO valves not installed | BLF to install them, Jacobs/Novartis to check the installationa dn the electrical wiring diagrams MCHR 16-MAR-2018: Loto valves installed for valve inside BLF scope | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | To perform passivation, the mechanical interlock on the Festo Clusters is removed to operate the valves. | BLF to check if some plastic interlocks have been damaged or lost and replace them / Fabiana Cortellini 02-AUG-2018: I/O check performed and no issues were communicated. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | All lines are identified with a temporary label; some of the components are identified with temporary label; Few components are not identified. | BLF to install final label on all the equipment/lines. / all components are temporary or permanently tagged; label to be done after insulation. / Refer to NC-11321 for the labeling. All the components are tagged. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-BUFFER-EG16N40-B204-O65 folio 1 of 2: tag of valves V005 and V952 swapped. | BLF to modify the temporary label. / Tag installed properly, according to the P&ID | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-RGS1-EG16C40-B204-O68: Burst disk not installed to avoid any damage. G811 instrument not installed. | BLF to complete installation. / Burst disk and sensor installed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 15-G/N2P-EG18X40-B204-O63: Line not installed. | BLF to installation the line. / Line installed; installation verified during WD1 with BLF according to the P&ID. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 40-ERFR-EG16C40-B204-O78: Missing connetion between Hose and tank. | BLF to installation the line. / Line completely installed and fixed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Line 50-CIP-EG16N40-B204-O89: missing a flange on the P&ID. | NVS to update the P&ID accordingly (rev. 3.1) / Refer to NC-0781 for the closure. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Line 20-AR-EG16C40-B204-407: Line not installed and ISO missing. | BLF to create the ISO and installation the line. / The ISO is part of the test pack of the fluid, it's not part of this system. For reference, see the corresponding test pack. For any non-conformity, check the fluid system. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 15-G/N2P- G18X40-B204-063: Line number on the Battery Limit missing. | BLF to update the ISO including the line number at the battery Limit (#163). BLF to generate new ISO for line #163 (empty ISO with reference). / The ISO is part of the test pack of the fluid, it's not part of this system. For reference, see the corresponding test pack. For any non-conformity, check the fluid system. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 20-RG1-EG16C40-B204-064: Line number on the Battery Limit missing; isometric continuity to RG3-PID1 wrong. | BLF to update the ISO including the line number at the battery Limit (#164). BLF to generate new ISO for line #164 (empty ISO with reference). / White ISOs created for the line; B.L. identified with correct number. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-BUFFER-EG16N40-B204-065 folio 2 of 2: continuity not accordig to P&ID. | BLF to update the ISO. / Iso updated accordingly. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 40-ACP-EG16N43-B204-067: Line number on the Battery Limit missing. | BLF to update the ISO including the line number at the battery Limit (#167). BLF to generate new ISO for line #167 (empty ISO with reference). / ISO has been updated with the correct line number as per P&ID; white ISO created and collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-RGS1-EG16C40-B204-068: Line number on the Battery Limit missing. | BLF to update the ISO including the line number at the battery Limit (#168). BLF to generate new ISO for line #168 (empty ISO with reference). / ISO has been updated with the correct line number as per P&ID; white ISO created and collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 15-ECR-EG16C40-B204-069: continuity not according to P&ID. | BLF to update the ISO. / ISO updated accordingly | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-BUFFER-EG16N40-B204-072: continuity not accordig to P&ID. | BLF to update the ISO. / ISO updated accordingly | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-CIPR-EG16N43-B204-073 folio 2 of 2: Line number on the Battery Limit missing. | BLF to update the ISO including the line number at the battery Limit (#206). BLF to generate new ISO for line #206 (empty ISO with reference). / ISO has been updated with the correct line number as per P&ID; white ISO created and collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-CIPR-EG16N43-B204-073 folio 2 of 2: wrong indication in the ISO table for the column QUANTITY | BLF to update the ISO. / ISO updated accordingly | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 40-ERF-EG16C40-B204-077: Line number on the Battery Limit missing. | BLF to update the ISO including the line number at the battery Limit (#177). BLF to generate new ISO for line #177 (empty ISO with reference). / ISO has been updated with the correct line number as per P&ID; white ISO created and collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 40-ERFR-EG16C40-B204-078: Wrong nozzle indication. | BLF to update the ISO / ISO updated accordingly | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-CIP-EG16N40-B204-089: continuity not accordig to P&ID. | BLF to update the ISO. / ISO updated accordingly | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Isometrics not conform to the P&ID: some lines indicated with different numbers. | NVS to update the P&ID accordingly (rev. 3.1): some line numbers to be deleted and some lines to be updated accordingly. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Reference on equipment list for Manual Ball Valve Mecainox cannot be verified on istalled valve. | BLF to verify and update the reference column in the equipment list. Fabiana Cortellini 26JAN2018: Reference is readable on the Datasheet only. PN4 is valves installed on hygienic pipes (valve is characterized by a greater length of the piece welded to the two sides of the body and by the incision on the body of the valve, as well as from the data of the roughness found on the pipe); PS4 is for the valves installed on non-hygienic pipes. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | 50-BUFFER-EG16N40-B204-065 folio 1 of 2: heat number missing. | BLF to update the ISO. Fabiana Cortellini 08-NOV-2017: Heat numbers have been added and checked. Refer to attached file. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | On the Equipment List line numbers not compliant with P&ID and few datasheet revision not compliant with the datasheets. | BLF to update Equipment List Fabiana Cortellini 09-NOV-2017: Equipment List has been updated in rev 1.07 and checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Weld numbers for the welds done directly on the skid (between two different isos) missing on the ISO. | BLF to update ISOs with the missing information. / All the ISOs are updated with the missing information. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | 40-ACP-EG16N40-B204-066 folio 1 of 2; reference on the equipment list for valve valve not possible to verify. | BLF to confirm the reference. / Reference have been checked by BLF and equipment list updated and attached to the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | 40-ACP-EG16N40-B204-066 folio 2 of 2: wrong tag for filter in the equipment list. | BLF to update the equipment list Fabiana Cortellini 08-NOV-2017: The filter tag has been updated on the Equipment List rev 1.06 and checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | 40-ACP-EG16N43-B204-067: missing heat number. | BLF to update ISO. Fabiana Cortellini 08-NOV-2017: Heat number has been added and checked. Refer to the attached document. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | 40-CIP-EG16N40-B204-071: wrong heat number. | BLF to update the related list. Fabiana Cortellini 08-NOV-2017: Heat number has been updated and checked. Refer to the attached document. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | 50-BUFFER-EG16N40-B204-072 folio 1 of 3; reference on the equipment list for bottom valve not possible to verify. | BLF to confirm the reference. / Reference have been checked by BLF and equipment list updated and attached to the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | 50-BUFFER-EG16N40-B204-072 folio 1 of 3: few heat numbers missing on isometric. | BLF to update the related list. / All the ISOs have been updated with the missing information. Refer to the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | 50-BUFFER-EG16N40-B204-072 folio 3 of 3: wrong heat number and one missing. | BLF to update the related list. 7 All the ISOs have been updated with the missing information. Refer to the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-CIPR-EG16N43-B204-073 folio 2 of 2: line not completely installed. | BLF to install the line on site. / Line installed, verification done according to the ISO; documentation collected into the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 15-ERF-EG1C40-B204-074: isometric not complete. | BLF to update iso. / ISO updated accordingly. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | risk assessment not available | BLF to provide the document. / Risk assessment availability is a test included into the SAT protocol. Refer to the SAT protocol for the test performing and conformity. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 40-CIP-EG16N40-B204-071 to be updated with the new flange added for handling reason. | BLF to update the ISO. / ISO updated accordingly | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | P&ID to be updated adding the new flange on line 40-CIP-EG16N40-B204-071 (for handling reason). | NVS to update the P&ID. / Comments included on the red marked P&ID. refer to NC- 0867 for the closure. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Welder qualification test certificate report YAL is missing. | Update the Welding book. Fabiana Cortellini 08-NOV-2017: The qualification test certificate report YAL is available and included in the welding book. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #H505, SG012, V806, V922, V930, V962, V963, V992, X101 and X811 : Certificate numbers missing hence unable to view VTOD. | BLF to update Equipment List BLF to include in VTOD Documentation for sight glass X111&X112 has been provided and checked this item is closed. H920,H922,H923 transferred to system VP2. V992 transferred to system B292. H505 transferred to AR system. V922,V930,V963 transferredto B293. Documentation checks for these items to be verified at SAT within the system that they have been transferred to. Angst/Pister X811 certificate numbers still missing from equipment list, unable to check documentation for these items. This action still outstanding. AWH to provide certificate of roughness as certificate not present in file Xo71 and Xo72 roughness certificate not identified on equipment list. Item X101, sampling port to be purchased by Novartis hence documentation for this item will be checked by Novartis. RCAR 07aug2018: X811 and X101 certificates collected in the VTOD Material Certificates and Equipment List updated accordingly. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item # X101 : Material certificate 3.1 is not identified on equipment list | Add Material Cert. in the VTOD and update the Equipment List Novaseptum X101 and Angst/Pister X811 certificate numbers still missing from equipment list, unable to check documentation for these items. Item X101, sampling port to be purchased by Novartis hence documentation for this item will be checked by Novartis. Freda burrows 02-Jul-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #XP102, P103, P500, X501 and X922 : Error on the equipment list. Material Certificate 2.1 is not available. | BLF to update Equipment List Fabiana Cortellini 08-NOV-2017: Material certificate 2.1 is covered by 3.1 certificate. No need to update the equipment list. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #X922 : FDA certificate not identified on equipment list | BLF to update Equipment List This item has been transferred to VP2. The documentation shall be checked within that system. see prolog number 0885 F Burrows 02-Jul-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #H920, H922, H923, V401, V503, X501 and X922 : BSE certificate missing on equipment list | BLF to update Equipment List Equipment list has been updated for V401, V503,X501 identifying BSE certificate on equipment list. H920, H922, H923,X922 shall be checked within the systems that the items have been transferred to see prolog number o885. F Burrows 02-Jul-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #V401, V503, X922, X071 and X072 : Roughness certificate not identified on equipment list | BLF to update Equipment List V401, V503, X922, have been transferred to other systems theequipment list shall be checked within the system that the items have been transferred to see prolog number 0885. Xo71 and Xo72 roughness certificate not identified on equipment list as certification is missing. Freda Burrows 02-Jul-2018 see prolog number 0885 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #V401, V503, X501 and X922 : EP certificate not identified on equipment list | BLF to update Equipment List Equipment list has been updated. F Burrows 10Jul2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #H922, H923, X922 and Y811 : Heat number not identified on equipment list | BLF to update Equipment List H922,H923,X922 have been removed documentation checks will be verified within the system that these items have been moved to. Heat numbers have been identified on equipment list. F Burrows 10-Jul-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Item #P102, P103, P500, V034, V401, V941, X501 and X504 : Heat number incorrect on equipment list | BLF to update Equipment List Heat numbers not checked since already recorded and checked during ISOs verification. The whole information is collected on a single page dedicated to each ISO and collected into the SAT protocol. F Burrows 10-Jul-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Technical documentation (manuals, operating instructions) missing for the equipments and instruments | Insert Technical documentation in the VTOD Tag number X811 documentation has not been provided for this equipment. This punch item is to be tracked via Prolog number 0885. Freda Burrows 10-Jul-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Isometrics for Line 40-VP2-EG16N44-B204-094, 8-VP2-EG16N44-B204-103 and 50-CIP-EG16N40-B204-189 are missing. | BLF to generate isometrics. Fabiana Cortellini 08-NOV-2017: Isometrics have been created, refer to attached documents. Isometrics to be checked on site, after pipes installation will be completed. Refer to NC-77. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50-BUFFER-EG16N40-B204-065 Folio 2, Welds #8, 9, 10, 11; ISO 15-ACP-EG16N43-046 Folio 1, Welds #1, 2, 3 : no access to conduct visual and video borescope checks | Welds to be checked by BLF and independent weld inspector to provide information. / Information have been provided by BLF. Inspector from Arcade has checked the welds on ACP line (S. Hilfinger) confirmed to BLF the welds are ok. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Test TS01.2.12 - Welding information missing from welding book for various welds on the following lines: weld #5 on ISO 10-ACP-EG16N40-B204-066 Folio 1/1 welds #1, 2, 3 and 4 on ISO 8-CIP-EG16N40-B204-071 Folio 1/1 | BLF to update welding book with the missing welding information and independent weld inspector (Arcade engineering) to perform the test. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | ISO 50 BUFFER-EG16N40-B204-072 Folio 1, Welds #1, 2, 3, 4 : Video borescope missing | BLF to provide the videos. / All the videos have been done again by BLF. Weld #2 has been checked directly by Arcade Inspector (S. Hilfinger) since video was still missing who confirmed the weld is ok. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Test TS01.2.12 - Weld executed on construction site for the following isometric; weld #5 and 6 on ISO 50-CIPR-EG16N43-B204-073 Folio 2/2 weld #300 on ISO 50-CIP-EG16N40-B204-070 Folio 1/1 | BLF to perform the weld on site and to update welding book with the information. Independent weld inspector (Arcade engineering) to examine the weld log document and validate all welding information. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | BSE/TSE free certificate and FDA (or USP) certificate missing for all the gaskets installed on pipes. | BLF to provide the certificates Seun Idowu 10-JUL-2018: The following material certificates have been included in VTOD: - P16-0052-FDA Gaskets-0001; - P16-0052-FDA Gaskets-0002. RCAR 07aug2018: the following are included in the VTOD: - P16-0052-FDA Gaskets-0003; - P16-0052-FDA Gaskets-0004. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | test not completely performed, gasket material not checked. | Check all gasket material according to pipeclass Seun Idowu 09-JUL-2018: Gasket material checked on isometric nomenclature document. Gasket material verified according to the Novartis specification document for each pipe class. EPDM or PTFE suitable for piping class EG16N43, EG16N44 and EG16N46. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | some heat numers missing on the isometric nomenclature document. | BLF to update the document. / ISO updated with all the information missing. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Test TS01.2.12 - on the weld log RTU-PR-S-121, the column C/NC (checked/non checked) is not ticked on the following isometrics: 50-BUFFER-EG16N40-B204-065 Folio 1/2 50-BUFFER-EG16N40-B204-065 Folio 2/2 10-ACP-EG16N40-B204-066 Folio 1/1 40-ACP-EG16N40-B204-066 Folio 2/2 40-ACP-EG16N43-B204-067 Folio 1/1 50-CIPR-EG16N43-B204-070 Folio 1/1 40-CIP-EG16N40-B204-071 Folio 1/1 50-CIPR-EG16N43-B204-073 Folio 1/2 50-CIPR-EG16N43-B204-073 Folio 2/2 50-CIP-EG16N40-B204-089 Folio 1/1 40-ACP-EG16N40-B204-127 Folio 1/1 | BLF to update weld log document RTU-PR-S-121 and independent weld inspector (Arcade engineering) to check the weld log document. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Line 40-CIP-EG16N40-B204-071: second flange to be added for maintenance of the flange already installed below valve V931. | Flange to be installed on site and local passivation to be performed. / Flange installed, ISO updated accordingly; passivation performed and documented (weld done 31-Jul; passivation done 4-Aug). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Safety clamp not installed on the top of the filter F1 (manometer nozzle). | BLF to install the safety clamp on site (manometer dismounted for transportation) / Manometer in place and Safety clamp installed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Pressure test on lines performed according to fluid list pressure values, but documentation missing. | BLf to provide the documentation. / documentation available. Verification has been done during SAT. Refer to the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Test TS01.2.03 - For the ISOs showing the battery limits, counter flange is not represented. BLF to update the ISOs showing the coulter flange and the relevant heat number. No weld indication must be represented (already represents in the piping contractor Isometrics). | BLF to update the ISO according to the installation. / Some flanges have been drawn dotted, some have been not drawn. Both situations are acceptable since the dotted flange is not in the vendor scope. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | As per WIN005 check completion of Passivation | 'Passivation performed. BLF to issue the documents related. A complete check as per WIN005 to ensure lines are passivated will be done. / Documentation available. Verification has been done during SAT according to the IV procedure. Refer to the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Test TS01.2.03 - For the ISOs showing the battery limits, counter flange is not represented. BLF to update the ISOs showing the coulter flange and the relevant heat number. No weld indication must be represented (already represents in the piping contracto | BLF to update the ISO according to the installation. Fabiana Cortellini 25-JUN-2018: Some flanges have been drawn dotted, some have been not drawn. Both situations are acceptable since the dotted flange is not in the vendor scope. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B205 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | As per WIN005 check completion of Passivation | Passivation performed. BLF to issue the documents related. A complete check as per WIN005 to ensure lines are passivated will be done. / Documentation available. Verification has been done during SAT according to the IV procedure. Refer to the SAT protocol. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Some components are not passivated by PG. | PG to provide a list of components that are not passivated by PG. (They could have been potentially passivated by the components supplier or not passivated at all). CCIA 03-mar-2018: the list has been provided by PG. All components are degreased and/or passivated by component supplier and/or by PG. Ref. attached documents (analysis done for bioreactors) | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | B206 - Buffer Storage Tank | LEVEL 1 | SAT | B | Building 341
0 | Passivation certificates check cannot be completed because piping installation is not completed aouside of the skids | Passivation certificates check to be completed on site after completion of installation and passivation CCIA 15-mar-2018: the test for passivation is formalized in the SAT protocol and will be fully executed. Ref R118_PSAT test 4.2.6 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Some components are not passivated by PG. | PG to provide a list of components that are not passivated by PG. (They could have been potentially passivated by the components supplier or not passivated at all). CCIA 03-mar-2018: the list has been provided by PG. All components are degreased and/or passivated by component supplier and/or by PG. Ref. attached documents (analysis done for bioreactors) | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R118 - Media Preparation Tank 2500L | LEVEL 1 | SAT | B | Building 341
0 | Passivation certificates check cannot be completed because piping installation is not completed aouside of the skids | Passivation certificates check to be completed on site after completion of installation and passivation CCIA 15-mar-2018: the test for passivation is formalized in the SAT protocol and will be fully executed. Ref R152_PSAT test 4.2.6 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | TSE/BSE Cetrificate for the whole centrifuge system to be provided by GEA Westfalia is missing | GEA Westfalia to provide TSE/BSE Cetrificate for the whole centrifuge system CCIA 24-Jan-2018: with reference to the attached decision the certificate is not necessary anymore | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R152 - Media Preparation Tank 10000L | LEVEL 1 | SAT | B | Building 341
0 | Heat gain calculation for power MCC cabinet is missing | GEA to provide relevant calculations CCIA 23-Jan-2018: documents provided | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | New WFI pressure reducer X910 has been installed replacing the previous one. | All relevant checks to be performed on the new components on site CCIA 20-feb-2018: all the requested relevant IV checks have been performed. refer attached files | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.1.7 foresees to check that PMI analysis has been performed on materials that are not covered by direct related certificate. This is the case for disks. These pieces are fabricated from row material SS 316L sheets. Raw materials are covered by certificates (not available at the moment), but GEA cannot guarantee from which specific raw sheets the disks are fabricated. According to test instructions and acceptance criteria, test is passed, also because the materials are the correct ones (316L / 1.4401-1.4404). This approach is deviating from requirement to have each material piece certified specific certificate for traceability purpose. First possibility GEA to provide set of certificates for stock of raw material and declaration from GEA that the disks are fabricated from this stock. Second possibility can be to exchange the full set of disks with one set singularly laser engraved to have direct reference to a certificate: Not to be considered Third possibility can be to re-perform PMI test 100%. Fourth possibility is to accept the percentage of PMI done by GEA (one disk checked each 10 disks + upper disk + lower disk): Not to be considered | GEA accepted to follow first possibility. GEA will produce: • Set of 3.1 certificates for raw materials • Extract from GEA SAP from which is possible to see the parts numbers (disks and spacers) • Declaration from GEA that all the parts listed (disks and spacer) installed in our machine are built from raw material certified with the set of certificates provided. GEA approach is accepted by NVS quality; ref. Muendges email dated 21-Jun-2017 12:18 “GEA to provide 3.1 certificates for a lot of metal sheets and confirmation (signed by Quality department) that the disks and spacers are made from this lot(s). CCIA 04-may-2018: GEA provided the requested declaration of compliance to Novartis specification for incoming goods inspection. Same, as GEA did for the Singapore centrifuge projects.ref attached documents | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | GEA is using lubricants on parts potentially in product contact. GEA is using grease in parts in product contact. GEA states also that especially greases cannot be avoided for normal functioning of the machine itself. | GEA to provide FDA and BSE/TSE free certificates. GEA to provide statement if degreasing is feasible or not. (ref. Jan Muendges email dated 20/06/2017 11:46) CCIA 24-apr-2018: Gea provided the FDA and BSE/TSE free certificates ref 9908_Satic SAT Protocol. Regarding the possibility to remove the grease it was stated several time that the grease is mandatory for the correct functioning as also specified in the Maintenance and Operating manual | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.2.2 GA drawing / Piping plan P1451648067-9908-3DM001 to be updated according to comments listed in the FAT protocol attachment 1 to test 7.2.2 | GEA to release new document revision F “as-built after FAT”. CCIA 23-Jan-2017: according to Novartis decision (email Fallet Claas dated 09-Jan-2018) not needed to updated as-built isometric drawings | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.2.3 Set of isometric drawings P1451648067-9908-ISO001/015 to be updated according to comments listed in the FAT protocol attachment 2 to test 7.2.2 | GEA to release new document revision “as-built after FAT”. CCIA 23-Jan-2017: according to Novartis decision (email Fallet Claas dated 09-Jan-2018) not needed to updated as-built isometric drawings | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.2.9 List of calibration certificates to be updated according to the comments of the attachment 1 of test 7.2.9 | GEA to release new document revision “as-built after FAT”. CCIA 25-apr-2018: as-built after fat has been issued and released. Ref. SAT protocol AT17 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | General Product inlet and outlet line to/from the centrifuge skid to be drained after production phase, pause water, water run (SIP?) | Assessment by Novartis (De Sousa, Larcher) is needed to understand if draining step has to be implemented. Details to be agreed with the User. Note from P. Larcher (27-Jun-2017): the last step after the V021 closing is buffer feed into the centrifuge, so the pipe will be full of buffer not product; this is acceptable. Final decision to be shared with F. De Sousa. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.3.1 UPS related devices labels shall be green background with white letters. | GEA to install correct ones CCIA 04-may-2018: labels have been installed correctly | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.3.1 Electrical wiring diagram to be updated according to comments on rev. F (re-test of FAT test 7.3.1) | GEA to issue the updated document, rev. G “As-built after FAT” | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.4.1 / 7.4.2 / 7.4.3 FDS to be updated according to comments on rev. B | GEA to issue the updated document CCIA / Chrappan 09-Jan-2018: the document has been updated. ref attached document | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | General / test 7.4.3 With reference to point n° 30, drainability test has been executed: Run 1 and Run 2 (ref. attachment n° 3 and n° 7 of test 7.4.3). | Novartis to assess the results of drainability tests and to advice if further actions are needed. Drainability results are acceptable. Nevertheless, the URS requirement for drainability has to be modified. (By C&Q team) | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.4.13 Maximum noise level measured at 1m from the machine is 81dBA, against a maximum acceptable value of 75dB (according to URS). | NVS to align internally on the acceptance, since GEA is stating that no action is possible on the machine itself CCIA 23-Jun-2017: with reference to Jan Muendges email dated 23-Jun-2016, deviation is accepted with the following rationale by (Amine Bellouki): “As discussed we keep the same philosophy of the site; meaning a pictogram of wearing hearing protection is mandatory on the box of centrifuge, and the box will have to be a soundproofing enclosure to reduce the noise level.” Follow-up actions are needed by NVS HSE (Action Bellouki): A. Bellouki 06.Mar.2018: The centrifuge will be inside the box in order to reduce the noise and any case the wearing of ear protection will be required inside the box of the centrifuge. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.3.10 According to the acceptance criteria the test is passed, nevertheless attachments #1 and #2 (set-up of parameters) to the test shall be included in the technical documentation according to VDR (Programmable devices set-up (including VFD)) | GEA to include the documents in the technical documentation | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.4.6 / 7.4.7 Document “Set point access authorization HMI” n° 8187-9058-938 to be updated according to comments on the document attached to test 7.4.6 | GEA to issue updated revision of the document | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.4.8 / 7.4.10 Test 7.4.8 “Check of recipe management” and test 7.4.10 “Check of batch report” are not applicable since the two functionalities are not requested for this machine. The two tests have not been performed during FAT (neither during PRE-FAT by GEA) | The two tests have to be removed from SAT protocol (Dynamic SAT protocol) CCIA 15-FEB-2018: point belonging to dynamic tests; transferred to C&Q | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.4.18 Documentation check according to agreed Index of documentation has negative results because documents are missing | 1. URS rev. 2.0 to be included 2. Contractual VDR to be included 3. Separator technical specification to be included 4. Device list rev. C to be included 5. Heat calculation for electrical cabinet to be included 6. Utilities consumption list to be included 7. Operating manual / Technical information / assembly drawing missing for Multiport Block Valve V910/V937 8. Instruction operating manual missing for Pall filter –F1 and –F2 9. Piping plan / GA drawing to be included in rev. F “as built after FAT” in A1 format 10. P&ID to be included in A1 format 11. Isometric set drawings to be included in rev. as built 12. Operating instruction manual to be filed under section 2.1/28 and not under 2.5 13. Documentation for proximity sensor, spray-ball, sight glass, cyclone level switch, vibration guard to be filed under section 2.1 and not under section 2.2 14. Panel / Control system hardware instruction manual to be provided 15. VFD parameter set-up to be included 16. Technical documentation / cut sheets missing for electrical components CCIA 24-Jan-2018: documents provided and checked. ref. attached file | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.4.18 Agreed index of documentation to be updated according to comments of attachment 1 to test 7.4.18 | GEA to update the index CCIA 11-Jan-2018: Index has been updated as per request. Ref attached file | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.4.18 Documentation check according to contractual VDR has negative results because documents are missing | 1. FDS to be included 2. Coloured flow P&IDs to be included 3. HDS to be included 4. SDS to be included 5. Datasheets and MSDS for lubricants to be included 6. Full list for Spare parts to be included 7. Special tools list / drawing 8. Equipment nameplate copy 9. Datasheet for all the o-rings and gaskets 10. Piping specification 11. COMOS datasheet for each component to be provided 12. Software source code back-up copy 13. SAT protocol 14. Equipment installation instructions / procedure and drawings to be provided 15. Software licences to be provided 16. As built version of 3D model to be provided CCIA 24-Jan-2018: documents provided and checked. ref. attached file | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.4.18 According to contractual VDR CE marking Declaration is needed. This certificate is missing for all components (mechanical / instruments / electrical). | GEA to provide CE marking Declaration for all the components CCIA 23-Jan-2018: this point is fully superseded and non needed considering the overall CE marking of the machine | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.4.18 According to VDR, after positioning and installation (by others), machine correct installation certificate is required by GEA | GEA to provide the document CCIA 12-feb-2018: the document is issued by Mediaco (handling and positioning company) and it certifies the adherence to the engineering documents about the correct positioning. Refer attached document. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.4.18 According to VDR the following procedures are missing: - Finishing and painting procedure specification - Grounding test procedure - Hydrostatic & Pneumatic test procedure - Cleaning & flushing procedure - Equipment passivation procedure - Mechanical polishing procedure specification - NDT Procedure | GEA to provide the documents CCIA 25-Jan-2018: GEA stated several times that the mentioned procedure cannot be released. They are available and can be checked in GEA offices. Point closed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.4.3 The software foresees that some signals / alarms are part of the “Common fault”. When Common fault occurs, the Centrifuge activates the step “shut down” that is part of the program “Normal Slowdown”. The normal shutdown doesn’t power off the VFD, but the VFD is commanded to generate a negative ramp in order to slowdown the motor quickly. In case the emergency push button is activated, the Centrifuge activates the step “shut down” that is part of the program “Slowdown for e-stop”. Slow down for e-stop powers off the VFD and this means that the motor is in inertial free rotation, and it stops rotating after a certain time. | Considering that this behaviour is mandatory for the good functioning of the machine, JI/NVS to check if the push button can be considered as an emergency device (since after its activation the motor still runs for a certain time); e.g. colour of the push button to be red or black. (action by Zwingelstein / Bellouki) A. Bellouki (06.Mar.2018): The motor will be protected according to machine directive and the maintenance will be executed following the site LOTO procedure. Note: there will be two emergency push buttons, one located on the door of the centrifuge cabinet inside the box and one located outside the box - exact location not defined yet, but outside anyway. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.4.5 (Check of Data Interface) Document Data Exchange List rev. D to be updated | GEA to issue updated document in revision E | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.1.8 With reference to att. 2 to tests 7.1.8 page 34 of 110 (drawing n° 3438-4323-019) a weld seam indication is missing. | GEA to add hand written correction to the welding documentation CCIA 31-Jan-2018: ref attached files | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.1.8 With reference to att. 2 to tests 7.1.8 page 37 of 110 (drawing n° 3438-4323-022) identification of manual weld instead of the orbital to be indicated | GEA to add hand written correction to the welding documentation CCIA 31-Jan-2018: ref attached files | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Test 7.1.9 Certificate of re-electropolishing of the hood after reworking of CIP inlet lines | GEA to provide the certificate CCIA 24-apr-2018: certificate of re-electropolishing provided. ref. 9908_Static SAT Protocol AT16 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Back-up of the software before internal tests and FAT starting is not formally mentioned by GEA | GEA to provide back-up of the software and to formalize them in the change log document. CCIA 29-may-2018: change log has been updated according to the requests. back-up of the software is not available anymore since overwritten. refer GEA statement here attached | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | Cold water Loopo, pressure test to be completed | Complete cold llop pressure test DRVP 30 APR 2018; Project agreement that no pressure testing required for main skid, only leak testing. To be completed as part of dynamic SAT. Chilled water pressure test to be completed under deviation No. 2500 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | F483 - Centrifuge | LEVEL 1 | SAT | B | Building 341
0 | BWT Tag numbers only no PO raised yet for Tags | Install Novartis Tag numbers | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | BWT Tag numbers only no PO raised yet for Tags | Install Novartis Tag numbers | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | BWT Tag numbers only no PO raised yet for Tags | Install Novartis Tag numbers | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | BWT Tag numbers only no PO raised yet for Tags | Install Novartis Tag numbers | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | BWT Tag numbers only no PO raised yet for Tags | Install Novartis Tag numbers | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EDP3-1 - Purified Water Generation & Storage System | LEVEL 1 | SAT | B | Building 341
0 | BWT P&IDs marked up at FAT. | Red line Comos PIDs with Prepare COMOS datasheets required FAT changes DRVP 22 Aug 2018; COMOS process master P&IDs red lined by Jacobs, NVS updated in COMOS, FR50-A02-900-EPI3-PID1 approved at rev 4.1 by NVS. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EDP3-1 - Purified Water Generation & Storage System | LEVEL 1 | SAT | B | Building 341
0 | BWT P&IDs marked up at FAT. | Red line Comos PIDs with Prepare COMOS datasheets required FAT changes DRVP 22 Aug 2018; COMOS process master P&IDs red lined by Jacobs, NVS updated in COMOS, FR50-A02-900-EPI3-PID2 approved at rev 4.0 by NVS. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | BWT P&IDs marked up at FAT. | Red line Comos PIDs with Prepare COMOS datasheets required FAT changes DRVP 22 Aug 2018; COMOS process master P&IDs red lined by Jacobs, NVS updated in COMOS, FR50-A02-900-EPI3-PID4 approved at rev 4.0 by NVS. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | BWT P&IDs marked up at FAT. | Red line Comos PIDs with Prepare COMOS datasheets required FAT changes DRVP 22 Aug 2018; COMOS process master P&IDs red lined by Jacobs, NVS updated in COMOS, FR50-A02-900-EDP3-PID1 approved at rev 4.1 by NVS. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | BWT P&IDs marked up at FAT. | Red line Comos PIDs with Prepare COMOS datasheets required FAT changes DRVP 22 Aug 2018; COMOS process master P&IDs red lined by Jacobs, NVS updated in COMOS, FR50-A02-900-EDP3-PID2 approved at rev 4.1 by NVS. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EDP3-1 - Purified Water Generation & Storage System | LEVEL 1 | SAT | B | Building 341
0 | BWT component datasheets relined at FAT | Prepare COMOS datasheets | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EDP3-1 - Purified Water Generation & Storage System | LEVEL 1 | SAT | B | Building 341
0 | BWT component datasheets relined at FAT | Prepare COMOS datasheets | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | BWT component datasheets relined at FAT | Prepare COMOS datasheets | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | BWT component datasheets relined at FAT | Prepare COMOS datasheets | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | BWT component datasheets relined at FAT | Prepare COMOS datasheets | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EDP3-1 - Purified Water Generation & Storage System | LEVEL 1 | SAT | B | Building 341
0 | Red mark on wiring diagram L61650.24.846A.001 rev 4 | Implement the red mark on next revision of wiring diagram. L61650.24.846A.001 wiring diagram updated and checked at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EDP3-1 - Purified Water Generation & Storage System | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on P&ID (attachment 1) L61650.23.846A.001 rev4 | Install missing tag numbers installed checked at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on P&ID (attachment 1) L61650.23.846A.001 rev4 | Change valve handle for V846A.8.1 to enable valve to be lockable. Agreed with NVS BWT to procure and install LOTO clamp shell. Lockable valve installed checked at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on P&ID (attachment 1) L61650.23.846A.001 rev4 | Update and reissue P&ID L61650.23.846A.001 L61650.23.846A.001 rev 5 issued at checked. Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on P&ID (attachment 1) L61650.23.846A.001 rev4 | Install missing counter flange and drain valve blanks counter flange and drain valve blanks installed and checked at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on component lists (see attachment 2 and 22) L61650.LOG.846A rev4 | Update and reissue Component list L61650.LOG.846A LOC issued and checked Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on component list (see attachment 4 and 23) L61650.LOG.846A rev4 | Obtain and insert missing manuals and datasheet. Correct file name of QE 846A.8.1 and QE846A.6.1 Updated stick file checked at SAT, all manuals present. Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on component list (see attachment 5 and 24) L61650.LOG.846A rev4 | Obtain missing certification include in final documentation certification checked in SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | L61650.846A.001 weld 10. Non conformamnce discolouration on section of HAZ | BWT to pickle and passivate and electropolish L61650.846A.001 weld 10, pickled and passivate and electropolish. Inspected prior to shipment to site Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Red mark on wiring diagram L61650.24.846B.001 rev 4 | Implement the red mark on next revision of wiring diagram. L61650.24.846B.001 wiring diagram updated and checked at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | No electrical Circuit for Green/red lamps on wiring diagram | Implement the Logic on wiring diagarm. Quotation from BWT required before implementation. Provide 24V DC output signal to drive red and green lamps (See Eric Von Kaenel email dated 24/08/2017) . Addition of relay and output terminals required. documentation updates required for wiring diagram, Hardware design spec, functional logic, data exchange list. (Not in original BWT scope, quotation to be provided). Closed , to be completed on multistill wiring diagram. Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Close command valve V846B3.3 not configured ninside software | Implement software functionality on PLC. Valve 846B3.3 close command to be configured. Updates required to software. Software changed, Francis Ziegelstrum email 04/09/2017. FL and DEC supplied 07/09/2017. Christophe Brand email 12/09/2017, OK in software. The Functional Logic (L61650-846B-FL-001 rev 5) and the Data Exchange (L61650-846B-dex-rev3-MPOPI) are OK. The number of revision of Data Exchange List header is incorrect. The Data Exchange List must be paged. The software history (L61650-M61650--SW-versionlog) is OK. Duncan Patterson 18-Jan-2018, punch complete see attached. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Signal V846B3.4.PID.SP2 offset not communicate with IP21 | Check software to find the bug. V846B3.1PID.SP2 offset address 284 not communicating correct value on DB. Check software datalink and address DB. Updates required to software. Software changed, Francis Ziegelstrum email 04/09/2017. FL and DEC supplied 07/09/2017. Christophe Barnd to review. Christophe Brand email 12/09/2017, OK in software. The address is correct in Data Exchange List (L61650-846B-dex-rev3-MPOPI) . The number of revision of Data Exchange List header is incorrect. The Data Exchange List must be paged. Duncan Patterson 18-Jan-2018 FAT 846B deviation 4 item closed. Closed, documentation updated and checked by Christophe Brand Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Valve on HMI wrongly tagged. V846B2.1 should be V561B.2.1 and V846B2.2 should be V561A.2.1 | Correct valve tag on HMI Valves on HMI to be retagged, V846B2.1 should be V561B.2.1, V846B2.2 should be V561A.2.1. Updates required to software. Software changed, Francis Ziegelstrum email 04/09/2017. FL and DEC supplied 07/09/2017. Christophe Brand email 12/09/2017, OK in HMI. The Functional Logic and the Data Exchange are OK. Duncan Patterson 18-Jan-2018 FAT 846B deviation 5 closed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Line test not complete L61650.846B.LT.001 rev 1 | Complete line test before starting SAT Closed, transffered to SAT doc no 61650-846B-SAT-Static-001 rev 03 deviation 9 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on P&ID (attachment 1) L61651.23.846B.001 rev5 | Install missing or amend tag numbers tag number installed and checked at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on P&ID (attachment 1) L61651.23.846B.001 rev5 | Change valve handle for V846B.8.1 to enable valave to be locakable. Agreed with NVS BWT to procure and install LOTO clamp shell. Lockable valve installed and checked at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on P&ID (attachment 1) L61651.23.846B.001 rev5 | Update and reissue P&ID, L61651.23.846B.001 L61651.23.846B.001 rev6 issued and checked Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on P&ID (attachment 1) L61651.23.846B.001 rev5 | Install missing counter flange and drain valve blanks. counter flanges and blinds installed, checked at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on component lists (see attachment 2 and 22) L61651.LOG.846B rev4 | Update component list, L61651.LOG.846B LOC issued and checked Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on component lists (see attachment 5 and 24) L61651.LOG.846B rev4 | Obtain and insert missing manuals and datasheets include in final documentation Updated stick file checked at SAT, all manuals present. Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on component lists (see attachment 4 and 23) L61651.LOG.846B rev4 | Obtain missing certification include in final documentation certification manual checked at SAT. Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on P&ID (attachment 29) T61650.23.561A.001 rev 4 | Update and reissue P&ID,T61650.23.561A.001 P&ID checked and marked up at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on P&ID (attachment 30) T61650.23.561B.001 rev 4 | Update and reissue P&ID,T61650.23.561B.001 P&ID checked and marked up at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Sanitization logic incorrect SQ53 (SANI1) temperature set at 85C with manual start. SQ54 (SANI2) temperature set at 130C with manual start and timer autostart. Closed, transferred to SAT doc no 61650-846B-SAT-Static-001 rev 03 deviation 11 Duncan Patterson 22-Feb-2018 | Change software and functional logic (L61650-846B-FL rev 4). Manaul start with timer autostart at 85C for cold loopo. Manual start at 130C for hot and cold Loopos Sanitization logic to be changed to; daily sanitization to be configured for 85C and Hot & Cold loop sanitization at 130C. HMI push button tags to be changed from SANI1 and SANI2 Software changed, Francis Ziegelstrum email 04/09/2017. FL and DEC supplied 07/09/2017. . Christophe Brand email 12/09/2017, OK for HMI button, the tags are changed. The logic to sanitization is present in the Functional Logic but the tags SANI1 and SANI2 are not changed. It’s the same in Data Exchange List. The rest of the documents are correct. In the Functional Logic and Data Exchange List, the valve number Novartis is not H531 but V531. Test to be completed at SAT | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Missing PW distribution loop valve (NVS tag V010) on M61650.24.438A.001 rev 4 | Add valve on wiring diagram M61650.24.438A.001 Solenoid valve to be installed in electrical panel. Pneumatic signal required to drive air to open valve. Updates required to software, documentation updates required for wiring diagram, functional logic, Data Exchange List Closed, transferred to SAT doc no 61650-438A-SAT-Static-001 rev 03 deviation 16 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-D(Fr) - Eau Pour Injection (Froid) | LEVEL 1 | SAT | B | Building 341
0 | Red mark comments on wiring digram M61650.24.438A.001 rev 4 | Revise and reissue wiring diagram M61650.24.438A.001 wiring diagram updated and checked at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Valves (NVS tag nos V931, V930, V250) are not managed in the distiller software(nether HMI or PLC) | (1) To correct PLC software, corrections to be verified during software FAT. (2) To correct HMI software Valves V438.4.15 (V931), V438.4.13 (V930) and V438.4.14 (V250) are not managed in the software (neither PLC or HMI) . Correct PLC and HMI software. Post FAT Software updated version tested 22/08/2017 ( L61650-M61650-R1) functionality of valves tested. Outstanding: software Data exchange table yet to be updated, no software history update in software. Documentation to be updated; functional logic, wiring diagram and Data Exchange List. FL and DEC supplied 07/09/2017. Christophe Barnd to review. Christophe Brand email 12/09/2017, The Functional Logic (M61650-438A-FL-001 rev 5)and the Data Exchange (M61650-438A-dex-rev3-user) are OK.T The software history is OK. The number of revision of Data Exchange List is incorrect. The Data Exchange List must be paged. The software history (L61650-M61650--SW-versionlog) is OK. wiring diagram yet to be revised. Duncan Patterson 18-Jan-2018 FAT 438A deviation 3 closed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Missing line tested to check | Complete line test and test before SAT Closed, transferred to SAT doc no 61650-438A-SAT-Static-001 rev 03 deviation 16 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Local/ remote functionality not as per requirement | Change the functionality as per requirements Local/remote mechanism not as per requirements. (See Christophe Brand email item 1). Updates required to software, documentation updates required for, functional logic, Data Exchange List. The management of the HMI (Enable/Disable) is not implemented as requested ( Automation_Standard API - IP21 . Test required, CB email 05/09/2017 Christophe Brand email 12/09/2017, review,The Functional Logic (M61650-438A-FL-001 rev 5)and the Data Exchange (M61650-438A-dex-rev3-user) are OK. The number of revision of Data Exchange List is incorrect. The Data Exchange List must be paged. The software history (L61650-M61650--SW-versionlog) is OK. Closed, transferred to SAT doc no 61650-438A-SAT-Static-001 rev 03 deviation 12 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Deviation as marked up on P&ID M61650.23.438A.001 rev 03 | Update and reissue M61650.23.438A.001 rev 03 P&ID updated and checked at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Deviation as marked up on P&ID M61650.23.438A.001 rev 03 | Add missing blank flanges to V38.7.1 and V438.3.2 Missing blanks added to flanges Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on component list. M61650.LOC.438A.001 rev 04. See attactments 2 and 22 | Update and reissue M61650.LOC.438A.001 rev 04 LOC issued and checked Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on component list. M61650.LOC.438A.001 rev 04. See attactments 5 | Obtain missing certificates inclide in final documentation Certification checked at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | See Christophe Brand email item 2). Additional Deviation found during functional logic testing 22/Aug/2017 There is no documentation available concerning the MPI exchange table (communication with Passerelle PLC to Delta V). Looking in the CPU_LOPA provided software file it seems this is handled in the DB450. Since there is no documentation provided for this exchange table (Data Exchange List) this table could not be verified during FAT | Update software. Christophe Brand email 05/09/2017, MPI exchange table on one PLC (CPU_LOPA). Necessary to define one table for each PLC (LOOP_845A, LOOP_846B and LOOP_845A). L61660.23.845A.001 rev 07 issued and checked Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on P&ID see attachment 1 and 18 L61660.23.845A.001 rev 06 FAT test 2.3.1, non critical | Update and reissue P&ID Duncan Patterson 18-Jan-2018, P&ID L61660.23.845A.001 updated to rev 07 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EPI3-G&S - EPI Generation & Storage | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on Components lists, see attachments 2 and 21 L61660_LOC_845A Rev 04 FAT test 2.3.3, non critical | Update component list, L61660_LOC_845A Duncan Patterson 18-Jan-2018 P&ID L61660_LOC_845A updated to Rev 05 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EDP3-1 - Purified Water Generation & Storage System | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on Components lists, see attachments 4 and 22 L61660_LOC_845A Rev 04 FAT test 2.3.4, non critical | Obtain and insert missing manuals and datasheets in final documentation CD Closed, transferred to SAT doc no 61660-845A-SAT-Static-001 rev 03 deviation 8 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EDP3-1 - Purified Water Generation & Storage System | LEVEL 1 | SAT | B | Building 341
0 | Missing or wrong information on wiring diagram, see attachment 9 L61660.24.845A.001 FAT test 2.4.1, non critical | Update and reissue wiring diagram, L61660.24.845A.001 wiring diagram updated and checked at SAT Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | EDP3-1 - Purified Water Generation & Storage System | LEVEL 1 | SAT | B | Building 341
0 | Data exchange list missing FAT test 2.5.2 and 2.5.3 non-critical | Issue data exchange list for 845A Data exchange list L61660-845-DEX rev 1 issued Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Deviations as marked up on P&ID see attachment 1 and 18 06166o.23.270A.001 rev 06 FAT test 2.3.1. Not critical | Update and reissue P&ID,06166o.23.270A.001 Duncan Patterson 18-Jan-2018 P&ID 06166o.23.270A.001 updated to rev 07 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341

## validation (hidden)
HVAC | JEG | jsmith
DCS | NOV | janderson
EMS | JAC | sbre
CS | NOX | bmarie
WFI | ZET | FCOR
PW | AXI | DRYA
ELE | BLF | MGRA
ACP | BLF1 | SMON
EMS | PG | CCIA
BMS | BWT | RMAR
R201 - Buffer Preparation Tank 12000L | GEA | DPAT
R221 - Buffer Preparation Tank 12000L | CLY | MQUA
F483 - Centrifuge | SPI | MMEN
B292 - CIP Skid & Distribution System (Buffer Preparation) | TPI | JVID
B591 - CIP Skid & Distribution System (DSP) | BLF6 | RCAR
B216 - Buffer Storage Tank | MER | MCEC
ELEC-Normal - Electrical (Normal: Distribution) | NOI | BCRU
R482 - CIP Skid Centrifuge | MOA | FBUR
B217 - Buffer Storage Tank | CLE | DBOI
B192 - CIP Skid & Distribution System (Media) | SNE | ARIV
B293 - CIP Skid & Distribution System (Buffer Storage) | EIF | SIDO
B215 - Buffer Storage Tank | SIE | RTOR
C446 - Bioreactor 15000L | REV | EDES
C447 - Bioreactor 15000L | SEN | MPOZ
R118 - Media Preparation Tank 2500L | ISS | MCHR
R152 - Media Preparation Tank 10000L | MED | FCOR
R481 - Harvest Pool Tank 18000L | EME | MLUI
EPI3-D(Fr) - Eau Pour Injection (Froid) | VIS | RODO
EPI3-G&S - EPI Generation & Storage | TRA | VSCH
B155 - Buffer Storage Tank |  | AZAI
B204 - Buffer Storage Tank |  | MBEC
B205 - Buffer Storage Tank |  | LBEN
B206 - Buffer Storage Tank |  | GCOL
B225- Buffer Storage Tank |  | SWEG
B226 - Buffer Storage Tank |  | MHAE
R263 - NaOH 0.5M Preparation Tank 2000L |  | AKEL
B493 - CIP Skid & Distribution System (USP) |  | FTOF
R205 - Buffer Preparation Tank 2000L |  | SCAL
R206 - Buffer Preparation Tank 12000L |  | EURO
R211 - Buffer Preparation Tank 12000L |  | DGOE
F635 - Nanofiltration |  | MROL
R645 - Ultrafiltration |  | GTAG
AR - Instrument Air Distribution System |  | CBOS
C433 - Seed Bioreactor 2500L |  | AHER
R480 - Intermediate Pool Tank 5000L |  | MLAS
VT62 - Makeup & Exhaust Units - Zones 3, D, C |  | VGIM
VT63 - Recirculation Unit - Zone 3 - System 2 |  | CFAL
VT64 - Recirculation Unit - Zone 3 - System 3 |  | LRE
VT67 - Makeup & Exhaust Units - Zone N.C. - System 10
VT67 - Makeup & Exhaust Units - Zone N.C. - System 6
EV/EVC - Potable Water Distribution System
B214 - Buffer Storage Tank
VT66 - Recirculation Unit - Zone C - System 5
B224 - Buffer Storage Tank
F480 - Clarification Skid
C413 - Seed Bioreactor 90L
C423 - Seed Bioreactor 450L
ECC - Hot Water for Heating
ECB - Biowaste Collection & Storage System
RGS - Vent Systems
ECE - Ethanol Waste Collection System
ERF - Chilled Water Generation and Distribution System
R264 - NaOH 0.1M Preparation Tank 6300L
R612 - Filtrate Pool Tank 5000L
DeltaV 4 - Process Control System (DeltaV)
DeltaV 1 - Process Control System (DeltaV)
R641 - Formulation Pool Tank 250L
R631 - Eluate Pool Tank 3800L
R650 - Eluate Pool Tank 3800L (Inactivation)
L702 - NaOH 30% Distribution System
R621 - Eluate Pool Tank 3800L
Zone NC - System 6 - Zone NC - System 6
VT61 - Makeup & Exhaust Units 2 - Zone 2 - System 1
VT60 - Makeup & Exhaust Units 1 - Zone 2 - System 1
K630 - Chromatography Skid III - K630
K620 - Chromatography Skid II - K620
K610 - Chromatography Skid I - K610
EPI - EPI Generation (Existing)
EDP3-1 - Purified Water Generation & Storage System
VT65 - Recirculation Unit - Zone D - System 4
V080 - Steam Distribution V8
EDP3-2 - Purified Water Distribution System
VT66 - Recirculation Unit - Zone C - System 11
ELEC - Emergency - Electrical (Emergency System)
EPI3-D(Ch) - EPI Distribution (Chaud)
EI - Firewater Distribution System
V050 - Steam Distribution V5
ELEC-UPS - Electrical (UPS)
IP21 - Room Monitoring System (RMS: InfoPlus 21) and non HVAC related utilities
DCS WDOG - DCS Watchdog
DECT - DECT System
Zone 3 - System 3 - Zone 3 - System 3
Zone D - System 4 - Zone D - System 4
CSA - Finishes - CSA - Finishes
341 - Building Management System (BMS) - HVAC control for Building 341
Zone 2 - System 1 - Zone 2 - System 1
ELEC - 20kV - 20kV Electrical System
R152-H3 - Elevating Platform (R152-H3)
X647 - Bags-Filling Station
R301 - NaOH Dilution Skid
C444 - Bioreacteur De Production 13500L
C445 - Bioreacteur De Production 13500L
C443 - Bioreacteur De Production 13500L
R001V400 - HVAC System for Pumping Station
R004U2XX - HVAC System for Electrical Substation - MV Room (0.04)
R003V400 - HVAC System for Electrical Substation - TR2 Room
ECR - Process Waste Collection & Storage System
Zone NC - Other
Fire Det - Fire Detection
R001U2XX - HVAC System for Electrical Substation - TGBT Room
Hoist - Hoist: Agitator & Drums 200L (R152)
F473 - Centrifugeuse
CNR - Condensate Collection System
B191 - CIP Acid Mixing Skid
Hoist - Hoist: Centrifuge Bowl / Parts (F483)
RDP - RDP screen for DeltaV
LAN-Plant - Plant LAN for DeltaV: printer, Backup & Recovery and antivirus server
CSA - Hoist: Drums 200L (R205) [R205-H1]
CSA - Hoist: Clarification Filters (F480) [F480-H1]
CSA - Hoist: Waste 1 [WASTE-H1]
341-A03 - Elevator (341-A03)
Zone C - System 5 - Zone C - System 5
Zone 3 - System 2 - Zone 3 - System 2
ACP - Process Air Distribution System
GN2P - G/N2P Distribution System
L711 - N2 Liquid Storage System
N459 - Manifolds