## punchlist
status | description | comments | date_orig | due_date | author_id | closure_id | supplier_id | system_id | floor_id | phase_id | cat_id | building_id | closed_by
0 | Calibration cert. roughnessmeter is missing | Insulation documents to be included in the DOE by BLF. / / Novartis decided to insulate the skid on site. Responsibility of a different vendor. No doc to be added into the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | 2nd Jacket side hydrostatic test is missing | Spray balls and diptubes documents to be included in the DOE by BLF Seun Idowu 15-MAY-2018: Spray balls and diptubes documents included in VTOD. Refer to R201 skid SAT protocol, section piping certificate material. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Notified Body's attestation is missing. This point is not blocking the MC. It's conditionally accepted by NVS management. | Change the revision on the material certificate list: BLF Seun Idowu 26-APR-2018: Material cert. list updated. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | CE confirmity from BLF is missing. This point is not blocking the MC. It's conditionally accepted by NVS management. | Gaskets documents to be included in the DOE by BLF / Certificates of manhole and handhole are available in the VTOD (ERIKS the supplier). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Maintenance log is missing | Update the welding book: BLF Seun Idowu 26-APR-2018: Welding map updated. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Notified Body's design examination is missing | Update the welding book: BLF Seun Idowu 26-APR-2018: Welding book updated. WPS #D190 included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | The following components are not installed: V503 - V941 - V401 - P101 - A1 - W101 - X111 - Y811 & G811 - L111 - P102 - X101 - T101. Only fitting, correct Supplier/Model/Type have been checked. | Accessory welding documents to be included in the DOE by BLF Seun Idowu 15-MAY-2018: Accessory welding documents included in VTOD. Refer to R201 skid SAT protocol, section piping welding report. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | The following components are missing: P111, dip-tube and sprayballs (3) | Degreasing/passivation certificate to be included in the DOE by BLF Seun Idowu 26-APR-2018: Internal and external degreasing/passivation certificates are included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | All tank nozzles and valves are not tagged | Flushing and drying certificate to be included in the DOE by BLF. Fabiana Cortellini 28-AUG-2018: Flushing is included in the passivation procedure. Drying executed but not documented. Accepted by NVS (Zanobini email 25aug2018). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Gaskets are all installed but some are damaged. | Electropolish certificate to be included in the DOE by BLF Seun Idowu 26-APR-2018: Electropolish procedure document is included in the DOE along with the other procedures. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Weldings information (heat number, ..) missing on the isometrics. Weld position not checked because diptube and sprayballs missing | Calibration certificate to be included in the DOE by BLF Seun Idowu 26-APR-2018: Calibration certificate roughnessmeter included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Line numbers wrong on ISO 50-BUFFER-EG16N40-R201-008 (bottom valve ISO) and line not tagged | Last hydraustatic test jacket side to be included in the DOE by BLF Fabiana Cortellini 20-JUN-2018: document fixed and included in the binder. Paper copy to be checked as soon as binder will be back on site. Category moved from A to B. / RCAR 03oct2018: document available in the VTOD Orange Binder. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Tag of light missing on P&ID | Notified Body's attestation to be included in the DOE by BLF / attestation available in the vtod | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Test functioning of agitator not performed because agitator not installed. | CE conformity to be included in the DOE by BLF / CE declaration by BLF is included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Test drainability not performed acccording to the family approach agreed (test performed on R211) | Maintenance log to be included in the DOE by Novartis / document included in the VTOD | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Test vessel level strapping not performed acccording to the family approach agreed (test performed on R206) | Notified Body's examination design to be included in the DOE by BLF Seun Idowu 26-APR-2018: Notified body (TUVRheinland) test report - examination of design included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Test sprayball coverage test not performed acccording to the family approach agreed (test performed on R211) | Components to be installed on site, after tank installation. Fabiana Cortellini 19-APR-2018: the following components have been installed and equipment list has been checked: V503 - V941 - V401 - P101 - A1 - L111 - P102 - X111 - T101. For W101, refer to item 9802. X101 to be installed by NVS (sampling not supplied by BLF). Y811 & G811 available (agreed that it will be given to C&Q team at mechanical completion). Not blocking MC. Fabiana Cortellini 18-JUL-2018: burst disk and sensor given to C&Q team. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Tolerance on diameter of ingold plugs not checked because final components not installed (sampling, conductivity, ..) | Components to be istalled on site, after tank installation. Fabiana Cortellini 28-MAR-2018: P111, sprayballs and diptube installed and checked during SAT. Refer to SAT protocol P16-0052-SAT MECHANICAL PROTOCOL R201. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Leak pressure test not performed | Final tags to be put in place on site, after tank installation Fabiana Cortellini 19-APR-2018: refer to prolog item 4823. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Jacket pipe to be cut to installl the tank in the final position through the penetration hole realized. | Gaskets to be replaced on site, after OQ completion Fabiana Cortellini 26-MAR-2018: refer to prolog point 8819. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Diptube and sprayballs missing | Information to be filled in after completion of weldings Fabiana Cortellini 28-MAR-2018: sprayballs and diptube checked during SAT. Refer to SAT protocol P16-0052-SAT MECHANICAL PROTOCOL R201. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Nameplate missing | Line to be tagged (after insulation) Fabiana Cortellini 19-APR-2018: ISO has been updated and checked during SAT. Refer to P16-0052-SAT MECHANINCAL PROTOCOL-R201. For insulation, refer to prolog item 8359. For missing tagging, refer to prolog item 4823. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Agitator and load cells not installed, no check done | P&ID to be updated Fabiana Cortellini 23-APR-2018: master copy of P&ID has been red-marked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | C | Building 341
0 | Some ingold plugs are damaged | Test to be performed during Commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Earthing lugs not found | Test to be performed during Commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Nuts of hadhole/sightglass damaged (just visual defect, no effect on functionality and no safety issue). | Test to be performed during Commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Studs (goujon) too shorts on some nozzles | Test to be performed during Commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Vessel drawing is not in 'As built' revision | Test to be checked during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Manufacturer's name plate is not available in the DOE | Test to be performed during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Insulation documents are not available | The pipe will be cut and re-weld later after the erection. Any necessary pressure test on the cooling line will be realized later with the pipes. / Pressure test performed and documented. All documents are collected into the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Spray ball and diptubes documents are missing | To be provided by BLF before MC. Electropolishing to be done after dynamic tests, to avoid scratches. Fabiana Cortellini 28-MAR-2018: sprayballs and diptube checked during SAT. Refer to SAT protocol P16-0052-SAT MECHANICAL PROTOCOL R221. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Material certificate list, items N14 and N15, drawing revision is 0.4 instead of 1.1 | BLF to install it on site. Temporary label must be installed prior shipment. / Nameplate in place. Indication according to the construction drawing. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Material certificate of gaskets are missing | Agitator and load cells to be installed on site Fabiana Cortellini 30-APR-2018: agitator has been installed and checked. Load cells not yet installed. Refer to prolog item 67. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Filler metal certificate number 1785 instead of 1787 | To be checked by BLF and replaced Fabiana Cortellini 08-JUN-2018: ingold plugs have been checked during SAT. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Welding log, weld #151 and 310 are not in the welds mapping | BLF to do it on the bracket to do in the same time the link from above to below the load cell and the grounding. Fabiana Cortellini 04-APR-2018: Earthing lugs have been installed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | WPS #D190 is missing (Weld #310) | Nuts to be exchanged on site Fabiana Cortellini 25-JUL-2018: nuts have been exchanged and checked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Welds #406A to D are missing in the welding log | BLF to check and exchange them on site Fabiana Cortellini 06-JUN-2018: studs have been exchanged by BLF on site, during the sprayball and diptube installation. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Accessory welding documents are missing | As built' revision to be included in the DOE by BLF Fabiana Cortellini 03-APR-2018: Construction drawing has been issued by BLF in rev 2.0, checked and approved with "no comment". | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Degreasing/passivation certificate is missing | Manufacturer's name plate to be included in the DOE by BLF/ Document available in the VTOD Orange Binder. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Flushing / drying procedure and certificates are missing | Insulation documents to be included in the DOE by BLF. / Novartis decided to insulate the skid on site. Responsibility of a different vendor. No doc to be added into the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Calibration cert. roughnessmeter is missing | Spary balls and diptubes documents to be included in the DOE by BLF Seun Idowu 15-MAY-2018: Spray balls and diptubes documents included in VTOD. Refer to R221 skid SAT protocol, section piping certificate material. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | 2nd Jacket side hydrostatic test is missing | Change the revision on the material certificate list: BLF. Fabiana Cortellini 14-DEC-2017: point copied from another tank, not valid for R221. No action required. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Notified Body's attestation is missing. This point is not blocking the MC. It's conditionally accepted by NVS management. | Gaskets documents to be included in the DOE by BLF / Document available in the VTOD Orange Binder. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | CE confirmity from BLF is missing. This point is not blocking the MC. It's conditionally accepted by NVS management. | Correction of the material list by BLF Seun Idowu 26-APR-2018: Material cert. list updated. Filler metal cert. number 1787 written on the material cert list. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Maintenance log is missing | Update the welding book: BLF Seun Idowu 26-APR-2018: Welding map updated. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Notified Body's design examination is missing | Update the welding book: BLF Seun Idowu 26-APR-2018: Welding book updated. WPS #D190 included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | The following components are not installed: V503 - V941 - V401 - P101 - A1 - W101 - X111 - Y811 & G811 - L111 - P102 - X101 - T101. Only fitting, correct Supplier/Model/Type have been checked. | Update the welding log: BLF Seun Idowu 26-APR-2018: Welding Log updated. Welds #406A to 406D deleted from the welding map and welding log (nameplate). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | The following components are missing: P111, dip-tube and sprayballs (3) | Accessory welding documents to be included in the DOE by BLF Seun Idowu 15-MAY-2018: Accessory welding documents included in VTOD. Refer to R221 skid SAT protocol, section piping welding report. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | All tank nozzles and valves are not tagged | Degreasing/passivation certificate to be included in the DOE by BLF Seun Idowu 26-APR-2018: Internal and external degreasing/passivation certificates are included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Gaskets are all installed but some are damaged. | Flushing and drying certificate to be included in the DOE by BLF. Fabiana Cortellini 28-AUG-2018: Flushing is included in the passivation procedure. Drying executed but not documented. Accepted by NVS (Zanobini email 25aug2018). | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Weldings information (heat number, ..) missing on the isometrics. Weld position not checked because diptube and sprayballs missing | Calibration certificate to be included in the DOE by BLF Seun Idowu 26-APR-2018: Calibration certificate roughnessmeter included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Line numbers wrong on ISO 221-3, 221-4, 221-5 and 50-BUFFER-EG16N40-R221-008 (bottom valve ISO) and line not tagged | Last hydrostatic test jacket side to be included in the DOE by BLF. Seun Idowu 26-APR-2018: Second Jacket side hydrostatic test included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Tag of light missing on P&ID | Notified Body's attestation to be included in the DOE by BLF / attestation available in the vtod | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Test functioning of agitator not performed because agitator not installed. | CE conformity to be included in the DOE by BLF / CE declaration by BLF available in the VTOD Orange Binder. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Test drainability not performed acccording to the family approach agreed (test performed on R211) | Maintenance log to be included in the DOE by Novartis / Document available in the VTOD Orange Binder. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | Test vessel level strapping not performed acccording to the family approach agreed (test performed on R206) | Notified Body's examination design to be included in the DOE by BLF Seun Idowu 26-APR-2018: "Notified body (TUVRheinland) test report - examination of design included in the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Test sprayball coverage test not performed acccording to the family approach agreed (test performed on R211) | Components to be installed on site, after tank installation. Fabiana Cortellini 19-APR-2018: the following components have been installed and equipment list has been checked: V503 - V941 - V401 - P101 - A1 - L111 - P102 - T101 - X111. Fro W101, refer to item 9803. X101 to be installed by NVS (sampling not supplied by BLF). Y811 & G811 available but not installed (agreed that it will be given to C&Q team at mechanical completion). Not blocking MC. Fabiana Cortellini 18-JUL-2018: burst disk and sensor given to C&Q team. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Tolerance on diameter of ingold plugs not checked because final components not installed (sampling, conductivity, ..) | Components to be istalled on site, after tank installation. Fabiana Cortellini 28-MAR-2018: P111, sprayballs and diptube installed and checked during SAT. Refer to SAT protocol P16-0052-SAT MECHANICAL PROTOCOL R221. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Leak pressure test not performed | Final tags to be put in place on site, after tank installation Fabiana Cortellini 30-APR-2018: refer to item 5022. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | Jacket pipe to be cut to installl the tank in the final position through the penetration hole realized. | Gaskets to be replaced on site, after OQ completion. Fabiana Cortellini 30-APR-2018: refer to item 9059. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed for the Instruments on the vessel. | Information to be filled in after completion of weldings Fabiana Cortellini 28-MAR-2018: sprayballs and diptube checked during SAT. Refer to SAT protocol P16-0052-SAT MECHANICAL PROTOCOL R221. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | IV - - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed for the Instruments on the vessel. | Line to be tagged (after insulation). Fabiana Cortellini 30-APR-2018: ISOs have been updated. For the missing labeling, refer to item 5022. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | IV - Component Datasheet IV execution (WIN004 Section 2.5) was not completed for the system. | P&ID to be updated Fabiana Cortellini 30-APR-2018:: master copy of P&ID has been red-marked. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | IV - Component Datasheet IV execution (WIN004 Section 2.5) was not completed for the system. | Test to be performed during Commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Test to be performed during Commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Test to be performed during Commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Testing IV execution WIN005 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Test to be performed during Commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Testing IV execution WIN005 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Test to be checked during SAT | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning / Passivation Testing IV execution WIN005 Section 2.5 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Test to be performed during commissioning | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning / Passivation Testing IV execution WIN005 Section 2.5 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | The pipe will be cut and re-weld later after the erection. Any necessary pressure test on the cooling line will be realized later with the pipes. / Pressure test performed and documented. All documents are collected into the VTOD. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | A | Building 341
0 | IV - Material Certification Review IV execution WIN005 Section 2.9 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 14-feb-2018: test 2.2 has been executed 100% during FAT. ref. att 5 of C446_PFATPIPING | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Material Certification Review IV execution WIN005 Section 2.9 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 14-feb-2018: test 2.2 has been executed 100%. refer att 3 of the C447_PFATPIPING | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID walkdown IV execution WIN004 Section 2.1 was not completed for Osmotron Pro 7.000 PW-2S Unit B | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 15-mar-2018: the execution of test 2.6 as requested is already requested in point 2475 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID walkdown IV execution WIN004 Section 2.1 was not completed for Loopo 450. | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 15-mar-2018: the execution of test 2.6 as requested is already requested in point 2480 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Slope check IV execution WIN004 Section 2.3 was not completed for the Osmotron Pro 7.000 PW-2S Unit B. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN004 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection file, test 2.1 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Slope check IV execution WIN004 Section 2.3 was not completed for the Loopo 450. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN004 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection file, test 2.1 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure tests IV execution WIN005 Section 2.1 was not completed for the Osmotron Pro 7.000 PW-2S Unit B. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection file, test 2.1 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure tests IV execution WIN005 Section 2.1 was not completed for the Loopo 450. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection file, test 2.1 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Flushing/blowdown IV execution WIN005 Section 2.3 was not completed for the Osmotron Pro 7.000 PW-2S Unit B. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.5 CCIA 14-feb-2018: with reference to PG vessel inspection file, test 2.5 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Flushing/blowdown IV execution WIN005 Section 2.3 was not completed for the Loopo 450. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.5 CCIA 14-feb-2018: with reference to PG vessel inspection file, test 2.5 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning/Passivation IV Execution WIN005 Section 2.5 was not completed for the Osmotron Pro 7.000 PW-2S Unit B. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.9 CCIA 13-feb-2018: test 2.9 has been executed according to PG assessed procedure. Moreover test 2.10 confirmation has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning/Passivation IV Execution WIN005 Section 2.5 was not completed for the Loopo 450. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.9 CCIA 13-feb-2018: test 2.9 has been executed according to PG assessed procedure. Moreover test 2.10 confirmation has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV Execution WIN005 Section 2.7 was not completed for the Osmotron Pro 7.000 PW-2S Unit B. | Corrective Action: Memo to be generated by S.M. Win 004 test 2.2 completed at SAT (100% P&ID walkdown). See SAT No: 61660-270A-SAT-Static-001 Rev 3, test 3.1.2: attachment 2 22/Feb/2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV Execution WIN005 Section 2.7 was not completed for the Loopo 450. | Corrective Action: Memo to be generated by S.M. Win 004 test 2.2 completed at SAT (100% P&ID walkdown). See SAT No: 61660-845A-SAT-Static-001 Rev 3, test 3.1.2: attachment 2 Closed 22-Feb-2018 Duncan Patterson | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Material Certification Review IV Execution WIN005 Section 2.9 was not completed for the Osmotron Pro 7.000 PW-2S Unit B. | Corrective action as specified by WIN004: Test 2.3 to be executed 100%. To be completed prior to Mechanical Completion. Win 004 test 2.4 completed at SAT (100% GMP slope walkdown). See SAT No: 61660-270B-SAT-Static-001 Rev 3, test 3.1.2: attachment 4 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Material Certification Review IV Execution WIN005 Section 2.9 was not completed for the Loopo 450. | Corrective action as specified by WIN004: Test 2.3 to be executed 100%. To be completed prior to Mechanical Completion. Win 004 test 2.4 completed at SAT (100% GMP slope walkdown). See SAT No: 61660-845A-SAT-Static-001 Rev 3, test 3.1.2: attachment 4 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID walkdown IV Execution WIN004 Section 2.1 was not completed for Osmotron 270A (X951). | Corrective action as specified by WIN005: Test 2.1 must be completed prior to Mechanical Completion. DRVP 30 APR 2018;Project agreement that no pressure testing required, only leak testing. To be completed as part of dynamic SAT. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Slope checks IV Execution WIN004 Section 2.3 was not completed for the Osmotron 270A (X951). | Corrective action as specified by WIN005: Test 2.1 must be completed prior to Mechanical Completion. DRVP 30 APR 2018; Project agreement that no pressure testing required, only leak testing. To be completed as part of dynamic SAT. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure tests IV Execution WIN005 Section 2.1 was not completed for the Osmotron 270A (X951). | Corrective action as specified by WIN005: Test 2.3 must be completed prior to Mechanical Completion. DRVP 30 APR 2018 Win 005 test 2.4 completed at SAT. See SAT No: 61660-270A-SAT-Static-001 Rev 3, test 3.1.5: attachment 12 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Flushing/blowdown IV Execution WIN005 Section 2.3 was not completed for the Osmotron 270A (X951). | Corrective action as specified by WIN005: Test 2.3 must be completed prior to Mechanical Completion. DRVP 05 Mar 2018; Comos P&ID marked up as per WIN 005 tests 2.4 and 2.6. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning/Passivation IV Execution WIN005 Section 2.5 was not completed for the Osmotron 270A (X951). | Corrective action as specified by WIN005: Test 2.5 must be completed prior to Mechanical Completion. Win 005 test 2.6 completed at SAT. See SAT No: 61660-270B-SAT-Static-001 Rev 3, test 3.1.5: attachment 12 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation IV Execution WIN005 Section 2.7 was not completed for the Osmotron 270A (X951). | Corrective action as specified by WIN005: Test 2.5 must be completed prior to Mechanical Completion. DRVP 05 Mar 2018; COMOS P&IID marked up as per WIN 005 tests 2.4 and 2.6 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Material Certification IV Execution WIN005 Section 2.9 was not completed for the Osmotron 270A (X951). | Corrective action as specified by WIN005: Test 2.7 to be executed 100%. To be completed prior to Mechanical Completion. Win 005 test 2.8 (100% check) completed at SAT. See SAT No: 61660-270B-SAT-Static-001 Rev 3, test 3.1.5: attachment 8 and 9 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Testing IV Execution WIN005 Section 2.2 was not completed for the Centrifuge system F483. | Corrective action as specified by WIN005: Test 2.7 to be executed 100%. To be completed prior to Mechanical Completion. DRVP 30 APR 2018; WIN 5 test 2.8 completed see SAT 61660-845A-SAT-Static-001-Rev 3 attachments 8 and 9 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Flushing/blowdown IV Execution WIN005 Section 2.3 was not completed for the Centrifuge system F483. | Corrective action as specified by WIN005: Test 2.9 to be executed 100%. To be completed prior to Mechanical Completion. Win 005 test 2.10 (100% check) completed at SAT. See SAT No: 61660-270B-SAT-Static-001 Rev 3, test 3.1.5: attachment 8 and 10 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning/Passivation IV Execution WIN005 Section 2.5 was not completed for the Centrifuge system F483. | Corrective action as specified by WIN005: Test 2.9 to be executed 100%. To be completed prior to Mechanical Completion. Win 005 test 2.10 completed at SAT. See SAT No: 61660-845A-SAT-Static-001 Rev 3, test 3.1.5: attachment 8 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID walkdown IV Execution WIN004 Section 2.1 was not completed. | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. Win 004 test 2.2 completed at SAT (100% P&ID walkdown). See SAT No: 61660-270A-SAT-Static-001 Rev 3, test 3.1.2: attachment 2 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Verification of components IV Execution WIN004 Section 2.5 was not completed. | Corrective action as specified by WIN004: Test 2.4 to be executed 100%. To be completed prior to Mechanical Completion. Win 004 test 2.4 completed at SAT (100% GMP slope walkdown). See SAT No: 61660-270A-SAT-Static-001 Rev 3, test 3.1.2: attachment 4 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID walkdown IV Execution WIN004 Section 2.1 was not completed. | Corrective action as specified by WIN005: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. DRVP 30 APR 2018; Project agreement that no pressure testing required, only leak testing. To be completed as part of dynamic SAT. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Verification of components IV Execution WIN004 Section 2.5 was not completed. | Corrective action as specified by WIN005: Test 2.4 to be executed 100%. To be completed prior to Mechanical Completion. DRVP 30 APR 2018; Win 005 test 2.4 completed at SAT. See SAT No: 61660-270A-SAT-Static-001 Rev 3, test 3.1.5: attachment 12 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID walkdown IV Execution WIN004 Section 2.1 was not completed. | Corrective action as specified by WIN005: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. Win 005 test 2.6 completed at SAT. See SAT No: 61660-270A-SAT-Static-001 Rev 3, test 3.1.5: attachment 12 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Verification of components IV Execution WIN004 Section 2.5 was not completed. | Corrective action as specified by WIN005: Test 2.8 to be executed 100%. To be completed prior to Mechanical Completion. Win 005 test 2.8 (100% check) completed at SAT. See SAT No: 61660-270A-SAT-Static-001 Rev 3, test 3.1.5: attachment 8 and 9 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID walkdown IV Execution WIN004 Section 2.1 was not completed. | Corrective action as specified by WIN005: Test 2.10 to be executed 100%. To be completed prior to Mechanical Completion. Win 005 test 2.10 (100% check) completed at SAT. See SAT No: 61660-270A-SAT-Static-001 Rev 3, test 3.1.5: attachment 8 and 10 Duncan Patterson 22-Feb-2018 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Verification of components IV Execution WIN004 Section 2.5 was not completed. | Corrective action as specified by WIN005: Test 2.3 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 31-Jan-2018: P&ID of pressure test for separator and piping have been produced by Gea Westfalia. P&ID has been also highlighted for confirmation tests in FAT protocol. Ref attached files | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Test IV execution WIN005 Section 2.1.4 (Vessel Only) was not completed. | Corrective action as specified by WIN005: Test 2.4 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 31-Jan-2018: flushing and blowdaown is part of the cleaning and passivation procedure. Ref P&ID highlighted for tests 2.5 and 2.6. Ref. attached files | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Flushing / Blowdown IV execution WIN005 Section 2.3.4 (Vessel Only) was not completed. | Corrective action as specified by WIN005: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning/Passivation IV execution WIN005 Section 2.5.4 (Vessel Only) was not completed. | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. Fabiana Cortellini 04-JAN-2018: test 2.2 has been executed 100% according to WIN004. Refer to FAT protocols P16-0052-FAT-VESSEL-PROTOCOL-R201 and P16-0052-FAT-SKID-PROTOCOL-R201. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Test IV execution WIN005 Section 2.1.4 (Vessel Only) was not completed. | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. Fabiana Cortellini 04-JAN-2018: test 2.6 has been executed 100% (using datasheets or equipment list) according to WIN004. Refer to FAT protocols P16-0052-FAT-VESSEL-PROTOCOL-R201 and P16-0052-FAT-SKID-PROTOCOL-R201. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Flushing / Blowdown IV execution WIN005 Section 2.3.4 (Vessel Only) was not completed. | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. Fabiana Cortellini 04-JAN-2018: test 2.2 has been executed 100% according to WIN004. Refer to FAT protocols P16-0052-FAT-VESSEL-PROTOCOL-R205 and P16-0052-FAT-SKID-PROTOCOL-R205. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning/Passivation IV execution WIN005 Section 2.5.4 (Vessel Only) was not completed. | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. Fabiana Cortellini 04-JAN-2018: test 2.6 has been executed 100% (using datasheets or equipment list) according to WIN004. Refer to FAT protocols P16-0052-FAT-VESSEL-PROTOCOL-R205 and P16-0052-FAT-SKID-PROTOCOL-R205. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Test IV execution WIN005 Section 2.1.4 (Vessel Only) was not completed. | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. Fabiana Cortellini 04-JAN-2018: test 2.2 has been executed 100% according to WIN004. Refer to FAT protocols P16-0052-FAT-VESSEL-PROTOCOL-R211 and P16-0052-FAT-SKID-PROTOCOL-R211. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Flushing / Blowdown IV execution WIN005 Section 2.3.4 (Vessel Only) was not completed. | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. Fabiana Cortellini 04-JAN-2018: test 2.6 has been executed 100% (using datasheets or equipment list) according to WIN004. Refer to FAT protocols P16-0052-FAT-VESSEL-PROTOCOL-R211 and P16-0052-FAT-SKID-PROTOCOL-R211. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning/Passivation IV execution WIN005 Section 2.5.4 (Vessel Only) was not completed. | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. Fabiana Cortellini 04-JAN-2018: test 2.2 has been executed 100% according to WIN004. Refer to FAT protocols P16-0052-FAT-VESSEL-PROTOCOL-R221 and P16-0052-FAT-SKID-PROTOCOL-R221. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Test IV execution WIN005 Section 2.1.4 (Vessel Only) was not completed. | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. Fabiana Cortellini 04-JAN-2018: test 2.6 has been executed 100% (using datasheets or equipment list) according to WIN004. Refer to FAT protocols P16-0052-FAT-VESSEL-PROTOCOL-R221 and P16-0052-FAT-SKID-PROTOCOL-R221. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Flushing / Blowdown IV execution WIN005 Section 2.3.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.1.4 Fabiana Cortellini 01-MAR-2018: test 2.2 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R201 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning/Passivation IV execution WIN005 Section 2.5.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.3.4 Fabiana Cortellini 01-MAR-2018: test 2.4 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R201 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Test IV execution WIN005 Section 2.1.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.5.4 Fabiana Cortellini 01-MAR-2018: test 2.6 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R201 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Flushing / Blowdown IV execution WIN005 Section 2.3.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.1.4 Fabiana Cortellini 07-MAR-2018: A complete check as per WIN005 to ensure lines are pressure tested will be performed during SAT. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R201 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning/Passivation IV execution WIN005 Section 2.5.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.3.4 Fabiana Cortellini 07-MAR-2018: A complete check as per WIN005 to ensure lines are flushed and dried will be performed during SAT. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R201 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Test IV execution WIN005 Section 2.1.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.5.4 Fabiana Cortellini 19-APR-2018: test 2.6 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R201 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Flushing / Blowdown IV execution WIN005 Section 2.3.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.1.4 Fabiana Cortellini 01-MAR-2018: test 2.2 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R206 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning/Passivation IV execution WIN005 Section 2.5.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.3.4 Fabiana Cortellini 01-MAR-2018: test 2.4 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R206 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Test IV execution WIN005 Section 2.1.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.5.4 Fabiana Cortellini 01-MAR-2018: test 2.6 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R206 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Flushing / Blowdown IV execution WIN005 Section 2.3.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.1.4 Fabiana Cortellini 07-MAR-2018: A complete check as per WIN005 to ensure lines are pressure tested will be performed during SAT. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R206 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning/Passivation IV execution WIN005 Section 2.5.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.3.4 Fabiana Cortellini 07-MAR-2018: A complete check as per WIN005 to ensure lines are flushed and dried will be performed during SAT. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R206 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Test IV execution WIN005 Section 2.1.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.5.4 Fabiana Cortellini 07-MAR-2018: A complete check as per WIN005 to ensure lines are passivated will be performed during SAT. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R206 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Flushing / Blowdown IV execution WIN005 Section 2.3.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.1.4 Fabiana Cortellini 01-MAR-2018: test 2.2 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R211 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning/Passivation IV execution WIN005 Section 2.5.4 (Vessel Only) was not completed. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.3.4 Fabiana Cortellini 01-MAR-2018: test 2.4 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R211 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - - P&ID Walkdown IV execution WIN004 Section 2.1 (Skid Only) was not completed correctly - Not "stamped" with IV reference. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.5.4 Fabiana Cortellini 01-MAR-2018: test 2.6 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R211 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - - P&ID Walkdown IV execution WIN004 Section 2.1.2 (Skid Only) was not completed correctly - P&ID not signed and dated. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.1.4 Fabiana Cortellini 07-MAR-2018: A complete check as per WIN005 to ensure lines are pressure tested will be performed during SAT. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R211 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - - Slope and Drainability IV execution WIN004 Section 2.3.4 (Skid Only) was not completed correctly - No "Stamp" on each isometric. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.3.4 Fabiana Cortellini 07-MAR-2018: A complete check as per WIN005 to ensure lines are flushed and dried will be performed during SAT. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R211 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - - Slope and Drainability IV execution WIN004 Section 2.3 (Skid Only) was not completed correctly - No dwg indicating skid datum's available. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.5.4 Fabiana Cortellini 07-MAR-2018: A complete check as per WIN005 to ensure lines are passivated will be performed during SAT. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R211 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - - Slope and Drainability IV execution WIN004 Section 2.3.9 (Skid Only) was not completed correctly - Isometric not signed and dated at each slope check. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.1.4 Fabiana Cortellini 01-MAR-2018: test 2.2 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R221 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - - Component Datasheet IV execution WIN004 Section 2.5.2 (Skid Only) was not completed correctly - Not "stamped" with IV reference. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.3.4 Fabiana Cortellini 01-MAR-2018: test 2.4 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R221 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - - Slope and Drainability IV execution WIN004 Section 2.3 (Skid Only) was not completed correctly - No dwg indicating skid datum's available. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.5.4 Fabiana Cortellini 01-MAR-2018: test 2.6 will be executed during SAT according to WIN005. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R221 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - - Slope and Drainability IV execution WIN004 Section 2.3 (Skid Only) was not completed correctly - Angles of 2 Way GEMU valves not recorded. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.1.4 Fabiana Cortellini 07-MAR-2018: A complete check as per WIN005 to ensure lines are pressure tested will be performed during SAT. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R221 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - - Slope and Drainability IV execution WIN004 Section 2.3 (Skid Only) was not completed correctly - Angles of Block valves not recorded. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.3.4 Fabiana Cortellini 07-MAR-2018: A complete check as per WIN005 to ensure lines are flushed and dried will be performed during SAT. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R221 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed for the Instruments on the vessel. | Corrective action P&ID to be highlighted indicating test boundary in accordance with WIN005 Section 2.5.4 Fabiana Cortellini 07-MAR-2018: A complete check as per WIN005 to ensure lines are passivated will be performed during SAT. Refer to SAT protocol P16-0052-SAT-002-Mechanical Protocol-R221 test TS01.2.14. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Component Datasheet IV execution (WIN004 Section 2.5) was not completed for the system. | Corrective Action: Test Reference to be added to P&ID in accordance with WIN004 procedure Section 2.1.2 Fabiana Cortellini 30JAN2018: the reference to WIN004 Section 2.1 is made directly in the FAT protocol, chapter 3.2 Test List. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective Action: P&ID to signed and dated in accordance with WIN004 procedure Section 2.1.2 Fabiana Cortellini 30JAN2018: P&ID walkdown has been executed 100% during FAT, according to WIN004. P&ID has been dated and signed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Testing IV execution WIN005 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective Action: Test Reference to be added to isometric in accordance with WIN004 procedure Section 2.3.4 Fabiana Cortellini 30JAN2018: Slope and drainability has been executed 100% during FAT, according to WIN004. Each isometric has been stamped. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning / Passivation Testing IV execution WIN005 Section 2.5 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective Action: Datum dwg to be generated in accordance with WIN004 procedure Section 2.3 / All the slopes have been checked again 100% by the vendor and 30% by JE for confirmation. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Material Certification Review IV execution WIN005 Section 2.9 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective Action: Each slope check to be signed and dated in accordance with WIN004 procedure Section 2.3.9 Fabiana Cortellini 30JAN2018: Slope and drainability has been executed 100% during FAT, according to WIN004. Each isometric has been dated and signed. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed for the Instruments on the vessel. | Corrective Action: Test Reference to be added to Component Summary List in accordance with WIN004 procedure Section 2.5.2 / Stamp not needed; in the index cross reference between test and IV. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Component Datasheet IV execution (WIN004 Section 2.5) was not completed for the system. | Corrective Action: Datum dwg to be generated in accordance with WIN004 procedure Section 2.3. / All the slopes have been checked again 100% by the vendor and 30% by JE for confirmation. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective Action: 2 way GEMU valve angles to be measured and the values recorded in accordance with WIN004 procedure Section 2.3.9 / All the slopes have been checked again 100% by the vendor and 30% by JE for confirmation. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Testing IV execution WIN005 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective Action: Block valve angles to be measured and the values recorded in accordance with WIN004 procedure Section 2.3.9 / All the slopes have been checked again 100% by the vendor and 30% by JE for confirmation. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning / Passivation Testing IV execution WIN005 Section 2.5 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 14-feb-2018: with reference to att 3 of R481_PFATPIPING and att 5 PFAT_R481V test 2.2 has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Material Certification Review IV execution WIN005 Section 2.9 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 14-feb-2018: with reference to att 3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21 of test 2.2 has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed for the Instruments on the vessel. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN004 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection file test 2.1 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Component Datasheet IV execution (WIN004 Section 2.5) was not completed for the system. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection file test 2.1 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.5 CCIA 14-feb-2018: with reference to PG vessel inspection file test 2.5 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Testing IV execution WIN005 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.9 CCIA 13-feb-2018: test 2.9 has been executed according to PG assessed procedure. Moreover test 2.10 confirmation has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning / Passivation Testing IV execution WIN005 Section 2.5 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 13-feb-2018: with reference to att 6 of FAT protocol C413_PFAT test 2.2 has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Material Certification Review IV execution WIN005 Section 2.9 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 13-feb-2018: with reference to att 2, 6, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21, 22, 27, 28, 29 of FAT protocol C413_PFAT test 2.6 has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed for the Instruments on the vessel. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN004 Test 2.1 CCIA 13-feb-2018: test 2.1 has been executed according to PG assessed procedure. ref. vessel inspection plan | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Component Datasheet IV execution (WIN004 Section 2.5) was not completed for the system. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.1 CCIA 13-feb-2018: test 2.1 has been executed according to PG assessed procedure. ref. vessel inspection plan | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.5 CCIA 13-feb-2018: test 2.5 has been executed according to PG assessed procedure. ref. vessel inspection plan | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Testing IV execution WIN005 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.9 CCIA 13-feb-2018: test 2.9 has been executed according to PG assessed procedure. Moreover test 2.10 confirmation has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning / Passivation Testing IV execution WIN005 Section 2.5 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 14-feb-2018: test 2.2 has been executed 100% during FAT. ref. att 4 to FAT protocol C423_PFAT | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Material Certification Review IV execution WIN005 Section 2.9 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 14-feb-2018: tests 2.6 has been executed 100% during FAT. Ref. att. 4, 6, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20,21, 22, 23, 24, 26, 27, 28 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed for the Instruments on the vessel. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN004 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection plan, test 2.1 has been executed according to assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Component Datasheet IV execution (WIN004 Section 2.5) was not completed for the system. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.1 CCIA 14-feb-2018: according to PG vessel inspection plan tests 2.1 has been executed according to assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.5 CCIA 14-feb-2018: according to PG vessel inspection plan tests 2.5 has been executed according to assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Testing IV execution WIN005 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.9 CCIA 13-feb-2018: test 2.9 has been executed according to PG assessed procedure. Moreover test 2.10 confirmation has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning / Passivation Testing IV execution WIN005 Section 2.5 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 14-feb-2018: with reference to att 18 of C433_PFAT test 2.2 has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Material Certification Review IV execution WIN005 Section 2.9 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 14-feb-2018: with reference to att 4, 18, 21, 22, 23, 24, 25, 26, 27, 28, 29, 30, 31, 32, 33, 34, 35, 36, 37, 38, 39, 40, 43, 44, 45 test 2.6 has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed for the Instruments on the vessel. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN004 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection plan, test 2.1 has been executed according to assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Component Datasheet IV execution (WIN004 Section 2.5) was not completed for the system. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection plan, test 2.1 has been executed according to assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.5 CCIA 14-feb-2018: with reference to PG vessel inspection plan, test 2.5 has been executed according to assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Testing IV execution WIN005 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.9 CCIA 13-feb-2018: test 2.9 has been executed according to PG assessed procedure. Moreover test 2.10 confirmation has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning / Passivation Testing IV execution WIN005 Section 2.5 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 13-feb-2018: Test 2.2 executed 100% during FAT ref att. 30 of FAT Protocol R118_PFAT. test for components check on vessel IV 2.6 has been executed 100%, ref att. 40 of FAT Protocol R118_PFAT. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Material Certification Review IV execution WIN005 Section 2.9 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 13-Feb-2018: test 2.6 has been executed 100%. ref. att 40 of FAT protocol R118_PFAT | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed for the Instruments on the vessel. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN004 Test 2.1 CCIA 13-feb-2018: test 2.1 has been correctly executed according the assessed PG procedure. ref. PG 310B - R118 MEDIA 2500L - CONFORMITY INSPECTION OF PIPING. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Component Datasheet IV execution (WIN004 Section 2.5) was not completed for the system. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.1 CCIA 13-feb-2018: test 2.1 has been executed according to assessed PG procedure. Refer R118 vessel inspection plan | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.5 CCIA 13-feb-2018: test 2.5 has been executed according to PG assessed procedure. refer R118 vessel inspection file. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Testing IV execution WIN005 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.9 CCIA 13-feb-2018: test 2.9 has been executed according to the assessed procedure. Nevertheless test 2.10 of confirmation has been executed 100%. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning / Passivation Testing IV execution WIN005 Section 2.5 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 13-feb-2018: P&ID walkdown has been executed 100% for all the piping available at FAT date. ref att 35 of FAT protocol R152_PFAT | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Material Certification Review IV execution WIN005 Section 2.9 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 13-feb-2017: component check with datasheets or with BOM was completed for the components available at the FAT. ref. ATT 36-37-38-39-40-41-45 of the FAT protocol R152_PFAT | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed for the Instruments on the vessel. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN004 Test 2.1 CCIA 13-feb-2018: test 2.1 has been executed according to PG assessed procedure. refer vessel inspection plan | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Component Datasheet IV execution (WIN004 Section 2.5) was not completed for the system. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.1 CCIA 13-feb-2018: test 2.1 has been executed according to PG assessed procedure. refer vessel inspection plan | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - P&ID Walkdown IV execution WIN004 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.5 CCIA 13-feb-2018: test 2.5 has been executed according to the assessed PG procedure. ref. vessel inspection plan. | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Pressure Testing IV execution WIN005 Section 2.1 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.9 CCIA 13-feb-2018: test 2.9 has been executed according to PG assessed procedure. Moreover test 2.10 confirmation has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Cleaning / Passivation Testing IV execution WIN005 Section 2.5 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 14-feb-2018: with reference to att 3 of R480_PFAT test 2.2 has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Material Certification Review IV execution WIN005 Section 2.9 (Vessel Only) was not completed as per the IV Procedure (Vendor procedure used). | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 14-feb-2018: with reference to att 3,4,17,18,19,20,21,22,23,24,25,26,27 of R480_PFAT test 2.6 has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN004 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection file test 2.1 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection file test 2.1 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.5 CCIA 14-feb-2018: with reference to PG vessel inspection file test 2.5 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R221 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.9 CCIA 13-feb-2018: test 2.9 has been executed according to PG assessed procedure. Moreover test 2.10 confirmation has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Corrective action as specified by WIN004: Test 2.2 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 14-feb-2018: with reference to att 3 the test 2.2 has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Corrective action as specified by WIN004: Test 2.6 to be executed 100%. To be completed prior to Mechanical Completion. CCIA 14-feb-2018: with reference to att 3,4,5,6,7,8,9,10,11,12,13,14 the test 2.6 has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN004 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection file test 2.1 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.1 CCIA 14-feb-2018: with reference to PG vessel inspection file test 2.1 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.5 CCIA 14-feb-2018: with reference to PG vessel inspection file test 2.5 has been executed according to PG assessed procedure | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM001) which confirms acceptability of Vendor procedure for WIN005 Test 2.9 CCIA 13-feb-2018: test 2.9 has been executed according to PG assessed procedure. Moreover test 2.10 confirmation has been executed 100% | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM002) which confirms acceptability of using the Cross referenced table "Welding Pack Documentation Approvals for Pierre Guerin". CCIA 13-feb-2018: Cross referenced table "Welding Pack Documentation Approvals for Pierre Guerin" has been used during FAT for vessel and skid ref. att. 19 C446_PFATPIPING | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM002) which confirms acceptability of using the Cross referenced table "Welding Pack Documentation Approvals for Pierre Guerin". CCIA 13-feb-2018: Cross referenced table "Welding Pack Documentation Approvals for Pierre Guerin" has been used during FAT for vessel and skid ref. att. 17 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM002) which confirms acceptability of using the Cross referenced table "Welding Pack Documentation Approvals for Pierre Guerin". CCIA 13-feb-2018: Cross referenced table "Welding Pack Documentation Approvals for Pierre Guerin" has been used during FAT for vessel and skid ref. att. 19 (PFAT_R481V) and att 29 (R481_PFATPIPING) | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM002) which confirms acceptability of using the Cross referenced table "Welding Pack Documentation Approvals for Pierre Guerin". CCIA 13-feb-2018: Cross referenced table "Welding Pack Documentation Approvals for Pierre Guerin" has been used during FAT for vessel and skid ref. att. 46 and 50 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341
0 | IV - Welding Documentation Review IV execution WIN005 Section 2.8 was not completed as per the IV Procedure. | Memo has been generated (Ref: FR50-A01-IVM002) which confirms acceptability of using the Cross referenced table "Welding Pack Documentation Approvals for Pierre Guerin". CCIA 13-feb-2018: Cross referenced table "Welding Pack Documentation Approvals for Pierre Guerin" has been used during FAT for vessel and skid ref. att. 48 and 52 | ﻿2019-11-27 | ﻿2019-11-27 | RCAR | RCAR | BLF | R201 - Buffer Preparation Tank 12000L | LEVEL 1 | SAT | B | Building 341

## validation (hidden)
HVAC | JEG | jsmith
DCS | NOV | janderson
EMS | JAC | sbre
CS | NOX | bmarie
WFI | ZET | FCOR
PW | AXI | DRYA
ELE | BLF | MGRA
ACP | BLF1 | SMON
EMS | PG | CCIA
BMS | BWT | RMAR
R201 - Buffer Preparation Tank 12000L | GEA | DPAT
R221 - Buffer Preparation Tank 12000L | CLY | MQUA
F483 - Centrifuge | SPI | MMEN
B292 - CIP Skid & Distribution System (Buffer Preparation) | TPI | JVID
B591 - CIP Skid & Distribution System (DSP) | BLF6 | RCAR
B216 - Buffer Storage Tank | MER | MCEC
ELEC-Normal - Electrical (Normal: Distribution) | NOI | BCRU
R482 - CIP Skid Centrifuge | MOA | FBUR
B217 - Buffer Storage Tank | CLE | DBOI
B192 - CIP Skid & Distribution System (Media) | SNE | ARIV
B293 - CIP Skid & Distribution System (Buffer Storage) | EIF | SIDO
B215 - Buffer Storage Tank | SIE | RTOR
C446 - Bioreactor 15000L | REV | EDES
C447 - Bioreactor 15000L | SEN | MPOZ
R118 - Media Preparation Tank 2500L | ISS | MCHR
R152 - Media Preparation Tank 10000L | MED | FCOR
R481 - Harvest Pool Tank 18000L | EME | MLUI
EPI3-D(Fr) - Eau Pour Injection (Froid) | VIS | RODO
EPI3-G&S - EPI Generation & Storage | TRA | VSCH
B155 - Buffer Storage Tank |  | AZAI
B204 - Buffer Storage Tank |  | MBEC
B205 - Buffer Storage Tank |  | LBEN
B206 - Buffer Storage Tank |  | GCOL
B225- Buffer Storage Tank |  | SWEG
B226 - Buffer Storage Tank |  | MHAE
R263 - NaOH 0.5M Preparation Tank 2000L |  | AKEL
B493 - CIP Skid & Distribution System (USP) |  | FTOF
R205 - Buffer Preparation Tank 2000L |  | SCAL
R206 - Buffer Preparation Tank 12000L |  | EURO
R211 - Buffer Preparation Tank 12000L |  | DGOE
F635 - Nanofiltration |  | MROL
R645 - Ultrafiltration |  | GTAG
AR - Instrument Air Distribution System |  | CBOS
C433 - Seed Bioreactor 2500L |  | AHER
R480 - Intermediate Pool Tank 5000L |  | MLAS
VT62 - Makeup & Exhaust Units - Zones 3, D, C |  | VGIM
VT63 - Recirculation Unit - Zone 3 - System 2 |  | CFAL
VT64 - Recirculation Unit - Zone 3 - System 3 |  | LRE
VT67 - Makeup & Exhaust Units - Zone N.C. - System 10
VT67 - Makeup & Exhaust Units - Zone N.C. - System 6
EV/EVC - Potable Water Distribution System
B214 - Buffer Storage Tank
VT66 - Recirculation Unit - Zone C - System 5
B224 - Buffer Storage Tank
F480 - Clarification Skid
C413 - Seed Bioreactor 90L
C423 - Seed Bioreactor 450L
ECC - Hot Water for Heating
ECB - Biowaste Collection & Storage System
RGS - Vent Systems
ECE - Ethanol Waste Collection System
ERF - Chilled Water Generation and Distribution System
R264 - NaOH 0.1M Preparation Tank 6300L
R612 - Filtrate Pool Tank 5000L
DeltaV 4 - Process Control System (DeltaV)
DeltaV 1 - Process Control System (DeltaV)
R641 - Formulation Pool Tank 250L
R631 - Eluate Pool Tank 3800L
R650 - Eluate Pool Tank 3800L (Inactivation)
L702 - NaOH 30% Distribution System
R621 - Eluate Pool Tank 3800L
Zone NC - System 6 - Zone NC - System 6
VT61 - Makeup & Exhaust Units 2 - Zone 2 - System 1
VT60 - Makeup & Exhaust Units 1 - Zone 2 - System 1
K630 - Chromatography Skid III - K630
K620 - Chromatography Skid II - K620
K610 - Chromatography Skid I - K610
EPI - EPI Generation (Existing)
EDP3-1 - Purified Water Generation & Storage System
VT65 - Recirculation Unit - Zone D - System 4
V080 - Steam Distribution V8
EDP3-2 - Purified Water Distribution System
VT66 - Recirculation Unit - Zone C - System 11
ELEC - Emergency - Electrical (Emergency System)
EPI3-D(Ch) - EPI Distribution (Chaud)
EI - Firewater Distribution System
V050 - Steam Distribution V5
ELEC-UPS - Electrical (UPS)
IP21 - Room Monitoring System (RMS: InfoPlus 21) and non HVAC related utilities
DCS WDOG - DCS Watchdog
DECT - DECT System
Zone 3 - System 3 - Zone 3 - System 3
Zone D - System 4 - Zone D - System 4
CSA - Finishes - CSA - Finishes
341 - Building Management System (BMS) - HVAC control for Building 341
Zone 2 - System 1 - Zone 2 - System 1
ELEC - 20kV - 20kV Electrical System
R152-H3 - Elevating Platform (R152-H3)
X647 - Bags-Filling Station
R301 - NaOH Dilution Skid
C444 - Bioreacteur De Production 13500L
C445 - Bioreacteur De Production 13500L
C443 - Bioreacteur De Production 13500L
R001V400 - HVAC System for Pumping Station
R004U2XX - HVAC System for Electrical Substation - MV Room (0.04)
R003V400 - HVAC System for Electrical Substation - TR2 Room
ECR - Process Waste Collection & Storage System
Zone NC - Other
Fire Det - Fire Detection
R001U2XX - HVAC System for Electrical Substation - TGBT Room
Hoist - Hoist: Agitator & Drums 200L (R152)
F473 - Centrifugeuse
CNR - Condensate Collection System
B191 - CIP Acid Mixing Skid
Hoist - Hoist: Centrifuge Bowl / Parts (F483)
RDP - RDP screen for DeltaV
LAN-Plant - Plant LAN for DeltaV: printer, Backup & Recovery and antivirus server
CSA - Hoist: Drums 200L (R205) [R205-H1]
CSA - Hoist: Clarification Filters (F480) [F480-H1]
CSA - Hoist: Waste 1 [WASTE-H1]
341-A03 - Elevator (341-A03)
Zone C - System 5 - Zone C - System 5
Zone 3 - System 2 - Zone 3 - System 2
ACP - Process Air Distribution System
GN2P - G/N2P Distribution System
L711 - N2 Liquid Storage System
N459 - Manifolds